| Eric Wong Machinery Transportation Pte Ltd | Lifting Plan / Permit to Work | LP/PTW-01 |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 13/02/2020 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  | Hoist down 1 unit machine from lorry chassis to the ground, insert rollers, shift and position into production at ground floor |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation |  | 37 Joo Koon Rd – Energy Pipeline Services Pte Ltd |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date/time of lifting operation |  | 14/02/2020 - 11:00 am |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Validity period of lifting operation |  | 1 day |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | 1 unit CNC machine |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  | 250 x 230 x 250 cm |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 6, 000 kg |  |  |  | Known weight |  |  |  |  | Estimated weight |  |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  |  |  |  | Determined by drawing |  |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Mobile crane |  |  |  |  |  |  | Lorry loader |  |  |  |  |  |
| LM/LE Registration No. |  |  | LM 084683X |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 12/09/2019 |  | Expiry date of certificate |  |  |  |  |  |  |  |  |  | 11/09/2020 |
| Max. Safe Working Load |  |  | 18, 560 kg |  |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 17.30 m |  |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 7 m |  |  |  | SWL at this radius |  |  |  |  | 10, 670 kg |  |  |  |
| Type of lifting gears |  |  | Wire sling |  |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 50 kg |  |  | SWL of lifting gear |  |  |  |  |  |  | 4ton x 4pcs |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 23/12/2020 |  |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others _____________________________ |  |  |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  |  | Qualification / Experience |  |  |  |  |  |
| Site Supervisor |  | Koh Ban San |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Zahari / Koh Ban San |  |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |  |
| Lifting Equipment Operator |  | Lim Poh Thiam / Lim Poh Soon |  |  |  |  |  |  |  | Qualified crane operator |  |  |  |  |  |
| Rigger/Signalman |  | Asfandi / Ali / Jamari / Hassan |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| Rigger/Signalman |  | Sing Kwok Liang / Malik / Hanifah |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| The lifting supervisor of this operation is: Name & Title: Zahari / Koh Ban San / Lifting Supervisor Signature: |  |  |  |  |  |  |  |  |  | Steps shall be taken to eliminate danger to personnel involved and others including barriers where appropriate. Tools box meeting to take place and lifting plan be communicated |  |  |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Lifting Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |  |  |
| 1.Deploy lorry loader at designated unloading area |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 2.Hoist down machine from lorry chassis |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 3.Lower down machine to near ground level |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 4.Insert rollers under machine bed |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 5.Transport machine into production area at ground floor |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 6.Position machine at the designated location |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 7.Unload machine from rollers and insert levelling pad under machine bed |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 8.Once job complete, team leader will instruct team to perform proper housekeeping |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| - Sketch of Zone of Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sketch of the initial pick-up location, load path and lay-down area (include any obstructions or equipment clashes that may occur and how they will be avoided) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  |  | Signature: |  |  |  |  | Date: 13/02/20 |  |  |  |  |  |  |
| Prepared by: Koh Ban San Designation: Lifting Supervisor |  |  |  | Signature: |  |  |  |  | Date: 13/02/20 |  |  |  |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  |  | Signature: |  |  |  |  | Date: 13/02/20 |  |  |  |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  |  | Signature: |  |  |  |  | Date: 13/02/20 |  |  |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |