| Eric Wong Machinery Transportation Pte Ltd | Lifting Plan / Permit to Work | LP/PTW |  |
| --- | --- | --- | --- |
|  |  | Rev: 00 | Date: 07/05/25 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  | Hoisting machine |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation |  | 20 Teban Garden Crescent – The Singapore Mint |  |  |  |  |  |  |  |  |  |  |
| Date/time of lifting operation |  | 22/05/25 - 09:30 am |  |  |  |  |  |  |  |  |  |  |
| Validity period of lifting operation |  | 1 days |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads to be Hoist |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | Grabener Press GK800 |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  | 305 x 190 x 310 cm |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 17, 000 kgs |  |  |  | Known weight |  |  | Estimated weight |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  |  | Determined by drawing |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Mobile crane |  |  |  |  |  |  | Lorry loader |  |  |
| LM/LE Registration No. |  |  | LM345988P |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | /25 |  | Expiry date of certificate |  |  |  |  |  |  | /26 |
| Max. Safe Working Load |  |  | 32, 200 kg |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 25.4 m |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 7 m |  |  |  | SWL at this radius |  |  | 27, 200 kg |  |  |
| Type of lifting gears |  |  | Wire sling |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 100 kg |  |  | SWL of lifting gear |  |  |  | 8ton x 4pcs |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 10/12/25 |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  |  | Qualification / Experience |  |  |
| Site Supervisor |  | Koh Ban San/Wong Yen Siong /Zahari / Ibrahim |  |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Koh Ban San/Wong Yen Siong/ Zahari / Ibrahim |  |  |  |  |  |  |  | Qualified lifting supervisor |  |  |
| Lifting Equipment Operator |  | Yap Chin Chye / Lim Poh Soon / Lim Poh Thiam / Norhalim |  |  |  |  |  |  |  | Qualified crane operator |  |  |
| Rigger/Signalman |  | Ahmad / Hanifah / Vignesh / Rizal / Sarawanan |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |
| Rigger/Signalman |  | Malik / Aziz / Sing Kwok Liang / Rahman |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |
| - Lifting Tasks |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |
| 1.Deployment of mobile crane at designated hoisting area |  |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 2.Set up crane with outriggers fully extended and resting on metal plate/ timber mats as base plate |  |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 3.Shift out machine form production to hoisting area |  |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 4.Crane operator to rotate crane towards machine to determine the exact distance and boom angle |  |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 5.Riggers to insert required lifting gears to crane hook and secured to machine rigging point |  |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 6.Once rigging work is done, signalman to give signal to crane operator to hoist up machine |  |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 7.Load machine onto wooden base |  |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 8.Pack to form a case |  |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 9.After packing, load up case onto customer arrange low bed |  |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 10.Secured case with lashing belt and choking wood |  |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 11.Once job complete, team leader will instruct the team to perform proper housekeeping |  |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 12.All debris will be clear and disposed |  |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 13.Job complete |  |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  |  | Signature: |  |  |  | Date: 07/05/25 |  |  |  |  |
| Prepared by: Wong Yen Siong Designation: Lifting Supervisor |  |  |  | Signature: |  |  |  | Date: 07/05/25 |  |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  |  | Signature: |  |  |  | Date: 07/05/25 |  |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  |  | Signature: |  |  |  | Date: 07/05/25 |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work |  |  |  |  |  |  |  |  |  |  |  |  |