| Eric Wong Machinery Transportation Pte Ltd | Lifting Plan / Permit To Work | LP/PTW |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Rev: 00 |  |  |  |
|  |  | Date: 17/11/23 |  |  |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  | Hoisting machine |  |  |  |  |  |  |  |  |  |
| Location of lifting operation |  | 6 Tuas Ave 18 - Rohag (S) Pte Ltd |  |  |  |  |  |  |  |  |  |
| Date/time of lifting operation |  | Est: 21/11/23 – 09:45 am |  |  |  |  |  |  |  |  |  |
| Validity period of lifting operation |  | 1 day |  |  |  |  |  |  |  |  |  |
| - Details of Loads to be Hoist |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | 1 unit VTL 1600 ATC |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  | 455 x 439 x 345 cm |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 20, 830 kgs |  |  |  | Known weight |  | Estimated weight |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  | Determined by drawing |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  | Mobile crane |  |  |  |  |  |  | Lorry loader |  |  |
| LM/LE Registration No. |  | LM474127P |  |  |  |  |  |  |  |  |  |
| Date of last certification |  | 27/04/23 |  | Expiry date of certificate |  |  |  |  |  |  | 26/04/24 |
| Max. Safe Working Load |  | 32, 500 kg |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  | 43.00 m |  |  |  |  |  |  |  |  |  |
| Intended load radius |  | 6 m |  |  | SWL at this radius |  |  |  | 26, 500 kg |  |  |
| Type of lifting gears |  | Wire/webbing sling |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  | 100 kg |  |  |  | SWL of lifting gear |  |  | 10ton x 4pcs |  |  |
| Certification of lifting gears |  | Yes No |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  | 08/01/24 |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  | Qualification / Experience |  |  |
| Site Supervisor |  | Wong Yen Siong / Koh Ban San / Zahari |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Wong Yen Siong / Koh Ban San / Zahari |  |  |  |  |  |  | Qualified lifting supervisor |  |  |
| Lifting Equipment Operator |  | Yeo Hock Cheng / Lim Poh Soon / |  |  |  |  |  |  | Qualified crane operator |  |  |
| Rigger/Signalman |  | Ibrahim / Ahmad / Malik / Aziz |  |  |  |  |  |  | Qualified rigger/signalman |  |  |
| Rigger/Signalman |  | Sing Kwok Liang / Hanifah / Rahman / Tanesh |  |  |  |  |  |  | Qualified rigger/signalman |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |
| - Lifting Tasks |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |
| 1.Deployment of lorry crane at designated hoisting area |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 2.Setting up of crane on site with outriggers fully extended and resting on metal plate as base plate |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 3.To hoist down case from container to the ground |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 4.To uncrate machine case and put aside |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 5.Crane operator to rotate crane towards machine |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 6.Riggers will attached required lifting gears to crane hook and secured onto machine rigging point |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 7.Once rigging work is done, signalman to give signal to crane operator to hoist up and detach machine from base |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 8.Swing crane and lower down machine to near ground level |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 9.Insert rollers under machine bed |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 10.Transport machine into factory premise |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 11.Position machine at temporary location |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 12.Unload machine from rollers and insert woodblock under machine bed |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 13.Once job complete, team leader will instruct the team to perform proper housekeeping |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| 14.All debris will be clear and disposed |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/Zahari |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  | Signature: |  |  |  | Date: 21/11/23 |  |  |  |  |
| Prepared by: Wong Yen Siong Designation: Lifting Supervisor |  |  | Signature: |  |  |  | Date: 21/11/23 |  |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  | Signature: |  |  |  | Date: 21/11/23 |  |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  | Signature: |  |  |  | Date: 21/11/23 |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work |  |  |  |  |  |  |  |  |  |  |  |