| Eric Wong Machinery Transportation Pte Ltd | Lifting Plan / Permit to Work | LP/PTW-01 |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 16/09/21 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  | Lifting of machine |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation |  | Simtech, Valley Block |  |  |  |  |  |  |  |  |  |  |  |
| Date/time of lifting operation |  | 25/09/2021 – 09:45 am |  |  |  |  |  |  |  |  |  |  |  |
| Validity period of lifting operation |  | 1 day |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads to be Hoist |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | 1 unit Hydraulic Press machine |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  | 180 x 170 x 450 cm |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 15, 000 kgs |  |  |  | Known weight |  |  | Estimated weight |  |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  |  | Determined by drawing |  |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Mobile crane |  |  |  |  |  | Lorry loader |  |  |  |  |
| LM/LE Registration No. |  |  | LM077126C |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 24/05/21 |  | Expiry date of certificate |  |  |  |  |  |  |  | 23/05/22 |
| Max. Safe Working Load |  |  | 18, 240 kg |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 15.20 m |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 5.6 m |  |  |  | SWL at this radius |  |  | 14, 800 kg |  |  |  |
| Type of lifting gears |  |  | Wire/shackle |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 100 kg |  |  | SWL of lifting gear |  |  |  |  | 4ton x 4pcs |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 14/12/21 |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  | Qualification / Experience |  |  |  |  |
| Site Supervisor |  | Koh Ban San/Wong Yen Siong /Zahari |  |  |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Koh Ban San/Wong Yen Siong/ Zahari |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |
| Lifting Equipment Operator |  | Lim Poh Soon/Lim Poh Thiam |  |  |  |  |  |  | Qualified crane operator |  |  |  |  |
| Rigger/Signalman |  | Ibrahim/ Ali/ Sing Kwok Liang/Rahman |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |
| Rigger/Signalman |  | Malik / Ahmad / Hanifah / Asfandi |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Lifting Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |
| 1.Deployment of 2 lorry crane at designated hoisting area |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong / Zahari |  |  |  |  |  |
| 2.Setting up of crane on site with outriggers fully extended and resting on metal plate/woodblock as base plate |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong / Zahari |  |  |  |  |  |
| 3.Shift out machine from workshop to hoisting area |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong / Zahari |  |  |  |  |  |
| 4.Riggers will attached all required lifting gears to crane hook which is to be secured onto machine hoisting point |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong / Zahari |  |  |  |  |  |
| 5.Once rigging work is done, signalman to give signal to crane operator to hoist up machine |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong / Zahari |  |  |  |  |  |
| 6.Using lorry crane to assist in laying down machine to horizontal position |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong / Zahari |  |  |  |  |  |
| 7.Hoist and load machine onto low-loader chassis |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong / Zahari |  |  |  |  |  |
| 8.Secured case with strapping belt prior to being transport to scrapyard for disposal |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong / Zahari |  |  |  |  |  |
| 9.Once job complete, team leader will instruct the team to perform proper housekeeping |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong / Zahari |  |  |  |  |  |
| 10.All debris will be clear and disposed |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong / Zahari |  |  |  |  |  |
| 11.Job complete |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong / Zahari |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  |  | Signature: |  |  |  | Date: 25/09/21 |  |  |  |  |  |
| Prepared by: Wong Yen Siong Designation: Lifting Supervisor |  |  |  | Signature: |  |  |  | Date: 25/09/21 |  |  |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  |  | Signature: |  |  |  | Date: 25/09/21 |  |  |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  |  | Signature: |  |  |  | Date: 25/09/21 |  |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work |  |  |  |  |  |  |  |  |  |  |  |  |  |