| Eric Wong Machinery Transportation Pte Ltd | Lifting Plan / Permit to Work | LP/PTW-01 |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 28/07/21 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  | Hoisting of machine |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation |  | 91 Tuas Ave 1 – SMC Mfg (S) Pte Ltd |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date/time of lifting operation |  | 03/08/2021 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Validity period of lifting operation |  | 1 day |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads to be Hoist |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | 1 unit Mytech NC Milling |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  | 1400 x 2030 x 2200 mm |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 3, 000 kgs |  |  |  | Known weight |  |  |  |  | Estimated weight |  |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  |  |  |  | Determined by drawing |  |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Mobile crane |  |  |  |  |  |  | Lorry loader |  |  |  |  |  |
| LM/LE Registration No. |  |  | LM084683X |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 27/07/21 |  | Expiry date of certificate |  |  |  |  |  |  |  |  |  | 26/07/22 |
| Max. Safe Working Load |  |  | 9, 440 kg |  |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 16.40 m |  |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 6 m |  |  |  | SWL at this radius |  |  |  |  | 7, 000 kg |  |  |  |
| Type of lifting gears |  |  | Wire/webbing sling, shackle |  |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 50 kg |  |  | SWL of lifting gear |  |  |  |  |  |  | 4ton |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 18/01/22 |  |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  |  | Qualification / Experience |  |  |  |  |  |
| Site Supervisor |  | Koh Ban San / Zahari |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Koh Ban San / Zahari |  |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |  |
| Lifting Equipment Operator |  | Ngamin / Norhalim |  |  |  |  |  |  |  | Qualified crane operator |  |  |  |  |  |
| Rigger/Signalman |  | Ali / Rahman |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| Rigger/Signalman |  | Malik / Hanifah / Jamari |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Lifting Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |  |  |
| 1.Deploy lorry loader at designated unloading area |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 2.Setting up of lorry loader with outriggers fully extended and resting on timber mats/woodblock as base plate |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 3.Attached all required lifting gears to crane hook and secure to machine hoisting point |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 4.Hoist down machine from lorry chassis and lower down to near ground level |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 5.Insert pallet truck under machine base |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 6.Transport machine into factory production area at ground floor |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 7.Position machine at the designated location |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 8.Unload machine rollers and insert levelling pad under machine bed |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 9.Once job complete, proper housekeeping will be done, all debris will be clear and disposed |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 10.Job complete |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  |  | Signature: |  |  |  |  | Date: 03/08/21 |  |  |  |  |  |  |
| Prepared by: Zahari Designation: Lifting Supervisor |  |  |  | Signature: |  |  |  |  | Date: 03/08/21 |  |  |  |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  |  | Signature: |  |  |  |  | Date: 03/08/21 |  |  |  |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  |  | Signature: |  |  |  |  | Date: 03/08/21 |  |  |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |