| Eric Wong Machinery Transportation Pte Ltd | Lifting Plan / Permit to Work | LP/PTW |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 12/11/24 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  | Hoisting machine |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation |  | 16 Seletar Aerospace JEP Precision Engineering Pte Ltd |  |  |  |  |  |  |  |  |  |  |
| Date/time of lifting operation |  | 18-22/11/24 - 09:45 am |  |  |  |  |  |  |  |  |  |  |
| Validity period of lifting operation |  | Estimate: 4-5 day |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads to be Hoist |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | E-1060V/6 |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  | 600 x 345 x 320 cm |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 31, 000 kgs |  |  |  | Known weight |  |  | Estimated weight |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  |  | Determined by drawing |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Mobile crane |  |  |  |  |  |  |  | Lorry loader |  |
| LM/LE Registration No. |  |  | LM439191X |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 25/04/24 |  | Expiry date of certificate |  |  |  |  |  |  | 24/04/25 |
| Max. Safe Working Load |  |  | 60, 700 kg |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 24.8 m |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 7 m |  |  |  | SWL at this radius |  |  |  | 40, 700 kg |  |
| Type of lifting gears |  |  | Wire/webbing sling |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 100 kg |  |  | SWL of lifting gear |  |  |  |  | 15ton x 4pcs |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 09/09/25 |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  |  |  | Qualification / Experience |  |
| Site Supervisor |  | Koh Ban San/Wong Yen Siong /Zahari / Ibrahim |  |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Koh Ban San/Wong Yen Siong/ Zahari / Ibrahim |  |  |  |  |  |  |  |  | Qualified lifting supervisor |  |
| Lifting Equipment Operator |  | Balaganesh / Lim Poh Soon / Lim Poh Thiam / Ngaimin |  |  |  |  |  |  |  |  | Qualified crane operator |  |
| Rigger/Signalman |  | Ahmad / Hanifah / Kughnanesswaran / Rizal |  |  |  |  |  |  |  |  | Qualified rigger/signalman |  |
| Rigger/Signalman |  | Malik / Aziz / Sing Kwok Liang / Rahman / Vignesh |  |  |  |  |  |  |  |  | Qualified rigger/signalman |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  | Yes No |  |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  | Yes No |  |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  | Yes No |  |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  | Yes No |  |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  | Yes No |  |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  | Yes No |  |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tasks |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |
| 1.Deployment of mobile/lorry crane at designated hoisting area |  |  |  |  |  |  |  | Wong Yen Siong/Koh Ban San/ Zahari/Ibrahim |  |  |  |  |
| 2.Set up crane with outriggers fully extended and resting on metal plate/ timber mats as base plate |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.Jack up machine and insert under rollers under machine bed |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.Shift out machine form production to hoisting area |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.Crane operator to rotate crane towards machine to determine the exact distance and boom angle |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.Riggers will attached required lifting sling to crane hook |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.Secured sling to machine rigging point |  |  |  |  |  |  |  |  |  |  |  |  |
| 8.Once rigging work is done, signalman to give signal to crane operator to hoist up machine |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.Load machine onto container |  |  |  |  |  |  |  |  |  |  |  |  |
| 10.Secured machine with lashing belt and choking wood |  |  |  |  |  |  |  |  |  |  |  |  |
| 11.Once job complete, team leader will instruct the team to perform proper housekeeping |  |  |  |  |  |  |  |  |  |  |  |  |
| 12.All debris will be clear and disposed |  |  |  |  |  |  |  |  |  |  |  |  |
| 13.Job complete |  |  |  |  |  |  |  |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  |  | Signature: |  |  |  | Date: 12-15/11/24 |  |  |  |  |
| Prepared by: Wong Yen Siong Designation: Lifting Supervisor |  |  |  | Signature: |  |  |  | Date: 12-15/11/24 |  |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  |  | Signature: |  |  |  | Date: 12-15/11/24 |  |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  |  | Signature: |  |  |  | Date: 12-15/11/24 |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work |  |  |  |  |  |  |  |  |  |  |  |  |