| ERIC WONG MACHINERY TRANSPORTATION PL | PTW - LIFTING PLAN | PTW-LP |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 03/10/24 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project: |  | Moving out/hoisting machine |  |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation: |  | 51 Corporation Rd – Avitron Pte Ltd |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of lifting operation: |  | 12-18/07/24 |  |  |  |  | Time of lifting operation: |  |  |  |  |  |  | 09:45 am |
| Validity period of lifting operation: |  | 6-7 day |  |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | Mazak V8 machine |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load |  | 735 x 375 x 390 cm |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 40, 000 kgs |  |  |  | Known weight |  |  |  |  | Estimated weight |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  |  |  |  | Determined by drawing |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Lorry crane |  |  |  |  |  |  |  | Mobile crane |  |  |  |
| LM/LE Registration No. |  |  | LM973145A |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 17/10/23 |  | Expiry date of certificate |  |  |  |  |  |  |  | 12/10/24 |  |
| Max. Safe Working Load |  |  | 75, 000 kg |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 73.00 m |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 10 m |  |  |  | SWL at this radius |  |  |  |  | 46, 000 kg |  |  |
| Type of lifting gears |  |  | Wire sling, shackle |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 100 kg |  |  | SWL of lifting gear |  |  |  |  |  | 15ton x 4pcs |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 18/09/24 |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  |  |  | Qualification / Experience |  |  |  |
| Lifting Supervisor |  | Wong Yen Siong / Koh Ban San / Zahari |  |  |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |
| Lifting equipment/Lorry crane Operator |  | Tan Chun Kiat / Lim Poh Soon / Lim Poh Thiam / Norhalim |  |  |  |  |  |  |  |  | Qualified crane operator |  |  |  |
| Rigger/Signalman |  | Ahmad / Ibrahim / Malik / Aziz / Kughanesswaran |  |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |
| Rigger/Signalman |  | Hanifah / Sing Kwok Liang / Rahman / Rizal |  |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |
| The lifting Supervisor of this lifting operation is: Name & Title: Wong Yen Siong / Koh Ban San Signature: |  |  |  |  |  |  |  |  |  |  | Steps shall be taken to eliminate danger to personnel involved and others including barriers where appropriate. |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground conditions | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Lifting Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |  |
| 1.Jack up and insert rollers under machine bed |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari |  |  |  |  |  |  |
| 2.Shift out machine to loading bay |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari |  |  |  |  |  |  |
| 3.Riggers to attached sling to crane hook |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari |  |  |  |  |  |  |
| 4.Secured sling to rigging point of machine |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari |  |  |  |  |  |  |
| 5.Mobile crane to hoist up machine slowly to check on balancing |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari |  |  |  |  |  |  |
| 6.When well balanced, hoist up and load machine onto wooden base for packing |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari |  |  |  |  |  |  |
| 7.Pack to form a case |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari |  |  |  |  |  |  |
| 8.After packing hoist and load up onto customer arranged container |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari |  |  |  |  |  |  |
| 9.Release all sling from case |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari |  |  |  |  |  |  |
| 10.Secured case with lashing belt and chocking wood |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari |  |  |  |  |  |  |
| 11.Transport out case to the designated location |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari |  |  |  |  |  |  |
| 12.Once job complete, team leader will instruct the team to perform proper housekeeping |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari |  |  |  |  |  |  |
| 13.All debris will be clear and disposed |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari |  |  |  |  |  |  |
| 14.Job complete |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari |  |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Name: Zailani |  |  |  | Signature: |  |  |  |  | Date: 12-18/07/24 |  |  |  |  |  |
| Prepared by: Name: Wong Yen Siong |  |  |  | Signature: |  |  |  |  | Date: 12-18/07/24 |  |  |  |  |  |
| Assessed by: Name: Kevin Wong |  |  |  | Signature: |  |  |  |  | Date: 12-18/07/24 |  |  |  |  |  |
| Approved by: Name: Eric Wong |  |  |  | Signature: |  |  |  |  | Date: 12-18/07/24 |  |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |