| Eric Wong Machinery Transportation Pte Ltd | Lifting Plan / Permit to Work | LP/PTW-01 |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 18/11/20 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  | To hoist up 1 unit equipment to 2nd floor by using platform and lorry loader |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation |  | 8 Tractor Rd – Excelitas Technologies Singapore Pte Ltd |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date/time of lifting operation |  | Estimate: 22 /12/2020 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Validity period of lifting operation |  | 1 day |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads to be Hoist |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | 1 unit Corp Robot |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  | 180 x 180 x 180 cm |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 600 kgs |  |  |  | Known weight |  |  |  |  | Estimated weight |  |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  |  |  |  | Determined by drawing |  |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Mobile crane |  |  |  |  |  |  | Lorry loader |  |  |  |  |  |
| LM/LE Registration No. |  |  | LM084683X |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 28/08/2020 |  | Expiry date of certificate |  |  |  |  |  |  |  |  |  | 27/08/2021 |
| Max. Safe Working Load |  |  | 17, 840 kg |  |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 17.30 m |  |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 8 m |  |  |  | SWL at this radius |  |  |  |  | 8, 600 kg |  |  |  |
| Type of lifting gears |  |  | Wire sling, shackle |  |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 3, 500 kg |  |  | SWL of lifting gear |  |  |  |  |  |  | 4ton x 4pcs |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 08/09/2021 |  |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  |  | Qualification / Experience |  |  |  |  |  |
| Site Supervisor |  | Koh Ban San / Zahari |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Koh Ban San / Zahari |  |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |  |
| Lifting Equipment Operator |  | Lim Poh Thiam / Norhalim |  |  |  |  |  |  |  | Qualified crane operator |  |  |  |  |  |
| Rigger/Signalman |  | Rahman / Ali / Ahmad |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| Rigger/Signalman |  | Malik / Hanifah / Asfandi |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Lifting Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |  |  |
| 1.Deploy lorry loader at designated hoisting area |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 2.Set up lorry loader on site with outriggers fully extended and resting on timber wood as base plate |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 3.Load equipment onto platform |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 4.Secured equipment onto platform with strapping belt |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 5.Hoist up platform together with equipment to 2nd floor shutter door opening |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 6.Secured platform onto building pillar with strapping belt to prevent from swinging outward |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 7.shift out equipment from platform |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 8.Position equipment at the designated location |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 9.Once job complete, team leader will instruct the team to perform proper housekeeping |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| 10.All debris will be clear and disposed |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |  |
| - Sketch of the zone of operation: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  |  | Signature: |  |  |  |  | Date: 22/12/20 |  |  |  |  |  |  |
| Prepared by: Zahari Designation: Lifting Supervisor |  |  |  | Signature: |  |  |  |  | Date: 22/12/20 |  |  |  |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  |  | Signature: |  |  |  |  | Date: 22/12/20 |  |  |  |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  |  | Signature: |  |  |  |  | Date: 22/12/20 |  |  |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |