| EWMTPL | PTW-LIFTING PLAN | LP- MS-01 |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 16/06/22 |
|  |  | Page 1 of 2 |  |

| 1. General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Location: Blk 4 Kaki Bukit Ave 1 #04-07 |  | Company: Moveon Technologies Pte Ltd |  |  |  |  |  |  |  |  | Process: Hoisting up machine to 4th floor |  |  |  |  |
| Date of lifting operation: 04/07/22 |  |  |  |  |  |  | Time of lifting operation: 09:30 am |  |  |  |  |  |  |  |  |
| 2. Details of Loads |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | 1 unit ACC63GX Grinder machine |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 2, 800 kgs |  |  |  |  |  |  | Known weight |  |  |  | Estimated weight |  |  |
| Overall dimensions of load: |  | 2740 x 2250 x 1850 mm |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  |  |  |  | Estimated |  |  |  | Determined by drawing |  |  |
| 3. Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Lorry crane |  |  |  |  |  |  |  | Mobile crane |  |  |  |  |
| LM/LE Registration No. |  |  | LM474127P |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 11/11/21 |  |  | Expiry date of certificate |  |  |  |  |  |  |  |  | 10/11/2022 |
| Max. Safe Working Load |  |  | 32, 500 kg |  |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 43.00 m |  |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 8 m |  |  |  |  | SWL at this radius |  |  |  | 13, 000 kg |  |  |  |
| Type of lifting gears |  |  | Wire sling |  |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 100 kg |  |  |  |  |  | SWL of lifting gear |  |  |  | 4ton x 4pcs |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 13/12/22 |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  |  |  |  | Standard hand signals Radio Others_______ |  |  |  |  |  |  |
| 5. Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  |  |  | Name |  |  |  |  |  |  | Qualification / Experience |  |  |  |  |
| Lifting Supervisor |  |  |  | Zahari / Ibrahim |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |
| Mobile/Lorry Crane Operator |  |  |  | Yeo Hock Cheng / Norhalim |  |  |  |  |  |  | Qualified crane operator |  |  |  |  |
| Rigger/Signalman |  |  |  | Jamari / Hanifah |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |
| Rigger/Signalman |  |  |  | Rahman / Ali / Abd Malik |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |
| The lifting Supervisor of this lifting operation is: - Name & Title: Zahari / Ibrahim / Lifting Supervisor - Signature: |  |  |  |  |  |  |  |  |  |  | Steps shall be taken to eliminate danger to personnel involved and others including barriers where appropriate. |  |  |  |  |
| 6. Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Floor conditions | Is the floor made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. Lifting Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations |  |  |  |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |
| 1.Deployment of mobile/lorry crane at the designated hoisting area |  |  |  |  |  |  |  |  |  |  | Zahari / Ibrahim |  |  |  |  |
| 2.Load machine onto platform |  |  |  |  |  |  |  |  |  |  | Zahari / Ibrahim |  |  |  |  |
| 3.Secured machine onto platform with strapping belt |  |  |  |  |  |  |  |  |  |  | Zahari / Ibrahim |  |  |  |  |
| 4.Attached required lifting gears onto crane hook and secured onto lifting point of platform |  |  |  |  |  |  |  |  |  |  | Zahari / Ibrahim |  |  |  |  |
| 5.Hoist up platform to 4th floor swing gate opening |  |  |  |  |  |  |  |  |  |  | Zahari / Ibrahim |  |  |  |  |
| 6.Stabilize platform effectively and ensure platform 3ft metal plate protruding is fully lean and rested on building opening slab |  |  |  |  |  |  |  |  |  |  | Zahari / Ibrahim |  |  |  |  |
| 7.Secured platform onto building railing/pillar with strapping belt to prevent swing outward |  |  |  |  |  |  |  |  |  |  | Zahari / Ibrahim |  |  |  |  |
| 8.Insert pallet truck under machine base |  |  |  |  |  |  |  |  |  |  | Zahari / Ibrahim |  |  |  |  |
| 9.Shift out from platform and transport into tenant premise |  |  |  |  |  |  |  |  |  |  | Zahari / Ibrahim |  |  |  |  |
| 10.Once job complete, team leader will instruct the team to perform proper housekeeping |  |  |  |  |  |  |  |  |  |  | Zahari / Ibrahim |  |  |  |  |
| 11.All debris will be clear and disposed |  |  |  |  |  |  |  |  |  |  | Zahari / Ibrahim |  |  |  |  |
| 12.Job complete |  |  |  |  |  |  |  |  |  |  | Zahari / Ibrahim |  |  |  |  |
| 8. Sketch of Zone of Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Refer to attached |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Name: Zailani |  |  |  |  | Signature: |  |  |  |  | Date: 04/07/22 |  |  |  |  |  |
| Prepared by: Name: Zahari |  |  |  |  | Signature: |  |  |  |  | Date: 04/07/22 |  |  |  |  |  |
| Assessed by: Name: Kevin Wong |  |  |  |  | Signature: |  |  |  |  | Date: 04/07/22 |  |  |  |  |  |
| Approved by: Name: Eric Wong |  |  |  |  | Signature: |  |  |  |  | Date: 04/07/22 |  |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |