| EWMTPL | PTW - LIFTING PLAN | LP- MS-01 |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 17/02/23 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project: |  |  | Moving out, hoisting machine for packing |  |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation: |  |  | 16 Seletar Aerospace Crescent – JEP Precision Engineering Pte Ltd |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of lifting operation: |  |  | 01-03/03/23 |  |  |  |  | Time of lifting operation: 09:30 am |  |  |  |  |  |  |  |
| Validity period of lifting operation: |  |  | 2-3 day |  |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  |  | Mazak FH6800 CNC |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load |  |  | 575 x 300 x 280 cm |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  |  | 19, 000 kg |  |  |  | Known weight |  |  |  |  | Estimated weight |  |  |  |
| Centre of gravity: |  |  | Obvious |  |  |  | Estimated |  |  |  |  | Determined by drawing |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  |  | Lorry crane |  |  |  |  |  | Mobile crane |  |  |  |  |  |
| LM/LE Registration No. |  |  |  | LM9457B |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  |  | 05/12/22 |  | Expiry date of certificate |  |  |  |  |  |  |  |  | 04/12/23 |
| Max. Safe Working Load |  |  |  | 30, 000 kg |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  |  | 19.40 m |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  |  | 5.70 m |  |  |  | SWL at this radius |  |  |  |  |  | 22, 515 kg |  |
| Type of lifting gears |  |  |  | Wire/webbing sling |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  |  | 50 kg |  |  | SWL of lifting gear |  |  |  |  |  |  | 10ton x 4pcs |  |
| Certification of lifting gears |  |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  |  | 08/01/24 |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  |  | Qualification / Experience |  |  |  |  |  |
| Ste / Lifting Supervisor |  | Koh Ban San/Wong Yen Siong |  |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |  |
| Lorry Loader Operator |  | Liew Soon Hwa / Yeo Ah Seng / Lim Poh Soon |  |  |  |  |  |  |  | Qualified crane operator |  |  |  |  |  |
| Rigger/Signalman |  | Ali / Ahmad / Ibrahim |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| Rigger/Signalman |  | Malik / Hanifah / Sing Kwok Liang |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| The Lifting Supervisor of this lifting operation is: - Name & Title: Koh Ban San / Wong Yen Siong - Signature: |  |  |  |  |  |  |  |  |  | Steps shall be taken to eliminate danger to personnel involved and others including barriers where appropriate |  |  |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground conditions | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Lifting Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations |  |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |  |
| 1.Jack up machine using hydraulic jack |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 2.Insert rollers under machine base |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 3.Shift out machine to loading bay |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 4.Attached sling to crane hook and secured onto rigging point of machine |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 5.Lorry loader to hoist up machine 1ft above ground to check on balancing |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 6.When well balanced, hoist up and load machine onto wooden base |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 7.Pack to form a case |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 8.After packing load up onto container |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 9.Secured case with lashing belt and choking wood |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 9.Once job complete, team leader will instruct the team to perform proper housekeeping |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 10.All debris will be clear and disposed |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 11.Job complete |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| - Sketch of Zone of Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sketch of the initial pick-up location, load path and lay-down area (include any obstructions or equipment clashes that may occur and how they will be avoided) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Name: Zailani |  |  |  |  | Signature: |  |  |  |  |  | Date: 01-03/03/23 |  |  |  |  |
| Prepared by: Name: Wong Yen Siong |  |  |  |  | Signature: |  |  |  |  |  | Date: 01-03/03/23 |  |  |  |  |
| Assessed by: Name: Kevin Wong |  |  |  |  | Signature: |  |  |  |  |  | Date: 01-03/03/23 |  |  |  |  |
| Approved by: Name: Eric Wong |  |  |  |  | Signature: |  |  |  |  |  | Date: 01-03/03/23 |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |