| EWMTPL | PTW - LIFTING PLAN | PTW-LP-01 |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 03/06/22 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project: |  |  | Hoisting machine |  |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation: |  |  | 180 A.M.K Ave 8 – Nanyang Polytechnic |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of lifting operation: |  |  | 09/06/22 |  |  |  |  | Time of lifting operation: 09:40 am |  |  |  |  |  |  |  |
| Validity period of lifting operation: |  |  | 1 day |  |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  |  | XO 55-700 CMM machine |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load |  |  | 178 x 148 x 186 cm |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  |  | 1, 458 kgs |  |  |  | Known weight |  |  |  |  | Estimated weight |  |  |  |
| Centre of gravity: |  |  | Obvious |  |  |  | Estimated |  |  |  |  | Determined by drawing |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  |  | Lorry crane |  |  |  |  |  | Mobile crane |  |  |  |  |  |
| LM/LE Registration No. |  |  |  | LM 500971N |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  |  | 22/04/22 |  | Expiry date of certificate |  |  |  |  |  |  |  |  | 20/04/23 |
| Max. Safe Working Load |  |  |  | 9, 760 kg |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  |  | 16.20. m |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  |  | 6 m |  |  |  | SWL at this radius |  |  |  |  |  | 7, 000 kg |  |
| Type of lifting gears |  |  |  | Webbing sling |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  |  | 50 kg |  |  | SWL of lifting gear |  |  |  |  |  |  | 2ton x 4pcs |  |
| Certification of lifting gears |  |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  |  | 23/09/22 |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  |  | Qualification / Experience |  |  |  |  |  |
| Site Supervisor |  | Zahari / Ibrahim |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Zahari / Ibrahim |  |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |  |
| Lorry crane Operator |  | Ngamin / Lim Boon Lay |  |  |  |  |  |  |  | Qualified crane operator |  |  |  |  |  |
| Rigger/Signalman |  | Malik / Ali / Rahman |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| Rigger/Signalman |  | Hanifah / Jamari / Samad |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| The lifting Supervisor of this lifting operation is: - Name & Title: Zahari / Ibrahim / Lifting Supervisor - Signature: |  |  |  |  |  |  |  |  |  | Steps shall be taken to eliminate danger to personnel involved and others including barriers where appropriate |  |  |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground conditions | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations |  |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |  |
| 1.Insert pallet truck under machine base |  |  |  |  |  |  |  |  | Ibrahim / Zahari |  |  |  |  |  |  |
| 2.Shift out machine to loading bay |  |  |  |  |  |  |  |  | Ibrahim / Zahari |  |  |  |  |  |  |
| 3.Attached sling to crane hook and secured onto machine hoisting point |  |  |  |  |  |  |  |  | Ibrahim / Zahari |  |  |  |  |  |  |
| 4.Lorry loader to hoist up machine onto wooden base for packing |  |  |  |  |  |  |  |  | Ibrahim / Zahari |  |  |  |  |  |  |
| 5.After packing, hoist up case and load onto lorry chassis |  |  |  |  |  |  |  |  | Ibrahim / Zahari |  |  |  |  |  |  |
| 6.Transport and deliver to Eric Wong warehouse |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.Once job complete, team leader to instruct team to perform proper housekeeping |  |  |  |  |  |  |  |  | Ibrahim / Zahari |  |  |  |  |  |  |
| 8.All debris will be clear and dispose |  |  |  |  |  |  |  |  | Ibrahim / Zahari |  |  |  |  |  |  |
| 9.Job complete |  |  |  |  |  |  |  |  | Ibrahim / Zahari |  |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Name: Zailani |  |  |  |  | Signature: |  |  |  |  |  | Date: 09/06/22 |  |  |  |  |
| Prepared by: Name: Ibrahim |  |  |  |  | Signature: |  |  |  |  |  | Date: 09/06/22 |  |  |  |  |
| Assessed by: Name: Kevin Wong |  |  |  |  | Signature: |  |  |  |  |  | Date: 09/06/22 |  |  |  |  |
| Approved by: Name: Eric Wong |  |  |  |  | Signature: |  |  |  |  |  | Date: 09/06/22 |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |