| EWMTPL | PTW - LIFTING PLAN | LP- MS-01 |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 26/10/2020 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project: |  | Hoisting of machines to 2nd floor |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation: |  | Blk 2024 Bukit Batok St 23 – Micronvision Precision (S) Pte Ltd |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of lifting operation: |  | 26/10/2020 – 01/10/2020 |  |  |  |  |  | Time of lifting operation: 09:45 am |  |  |  |  |  |  |  |
| Validity period of lifting operation: |  | 1 day |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | Star SA16 Auto Lathe machine |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load |  | 215 x 100 x 170 cm |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 1, 700 kgs |  |  |  |  | Known weight |  |  |  |  | Estimated weight |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  |  | Estimated |  |  |  |  | Determined by drawing |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  |  | Lorry crane |  |  |  |  |  | Mobile crane |  |  |  |  |  |
| LM/LE Registration No. |  |  |  | LM 084683X |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  |  | 28/08/2020 |  | Expiry date of certificate |  |  |  |  |  |  |  |  | 27/08/2021 |
| Max. Safe Working Load |  |  |  | 17, 840 kg |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  |  | 17.30 m |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  |  | 7.4 m |  |  |  | SWL at this radius |  |  |  |  |  | 10, 670 kg |  |
| Type of lifting gears |  |  |  | Wire sling, shackle |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  |  | 50 kg |  |  | SWL of lifting gear |  |  |  |  |  |  | 4ton x 4pcs |  |
| Certification of lifting gears |  |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  |  | 23/12/2020 |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  |  | Name |  |  |  |  |  |  | Qualification / Experience |  |  |  |  |  |
| Lifting Supervisor |  |  | Wong Yen Siong/Koh Ban San |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |  |
| Lorry crane Operator |  |  | Lim Poh Thiam / Norhalim |  |  |  |  |  |  | Qualified crane operator |  |  |  |  |  |
| Rigger/Signalman |  |  | Ali/Sing Kwok Liang/Ahmad |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| Rigger/Signalman |  |  | Hanifah/Asfandi/Malik |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| Rigger/Signalman |  |  |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| The lifting Supervisor of this lifting operation is: Name & Title: Wong Yen Siong / Koh Ban San / Lifting Supervisor Signature: |  |  |  |  |  |  |  |  |  | Steps shall be taken to eliminate danger to personnel involved and others including barriers where appropriate. Tool box meeting to take place and lifting plan be communicated. |  |  |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground conditions | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Lifting Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations |  |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |  |
| 1.Deployment of lorry loader at designated hoisting area |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 2.Setting up of lorry loader on site |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 3.Attached lifting gears to crane hook and secured to hoisting point of machine |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 4.Lorry loader to hoist up machine slowly to check on balancing |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 5.When well balanced, hoist up machine slowly to 2nd floor |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 6.Swing crane and lower down machine into corridor pathway |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 7.Insert pallet truck under machine base |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 8.Release all sling from machine |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 9.Shift and transport machine into tenant premise |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 10.Repeat process till all machine have been hoist up |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| 11.Job complete |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Name: Zailani |  |  |  |  | Signature: |  |  |  |  |  | Date: 26/10/20 – 01/11/20 |  |  |  |  |
| Prepared by: Name: Wong Yen Siong |  |  |  |  | Signature: |  |  |  |  |  | Date: 26/10/20 – 01/11/20 |  |  |  |  |
| Assessed by: Name: Kevin Wong |  |  |  |  | Signature: |  |  |  |  |  | Date: 26/10/20 – 01/11/20 |  |  |  |  |
| Approved by: Name: Eric Wong |  |  |  |  | Signature: |  |  |  |  |  | Date: 26/10/20 – 01/11/20 |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |