| EWMTPL | PTW-LIFTING PLAN | LP- MS-01 |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 08/02/23 |
|  |  | Page 1 of 2 |  |

| General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Location: Blk 2 Kaki Bukit Ave 1 #03-05 |  | Factory: PTS Technologies Pte Ltd |  |  |  |  |  |  |  |  | Process: Hoisting down oven from 3rd floor |  |  |  |  |  |  |
| Date of lifting operation: |  |  |  |  |  |  | 18/02/23 |  |  |  |  |  |  |  |  |  |  |
| Time of operation: |  |  |  |  |  |  | 09:00 am |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | 1 x oven |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 1, 000 kgs |  |  |  |  |  |  | Known weight |  |  |  | Estimated weight |  |  |  |  |
| Overall dimensions of load: |  | 220 x 200 x 160 cm |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  |  |  |  | Estimated |  |  |  | Determined by drawing |  |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  |  | Lorry crane |  |  |  |  |  |  | Mobile crane |  |  |  |  |  |  |
| LM/LE Registration No. |  |  |  | LM 406824P |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  |  | 13/12/22 |  | Expiry date of certificate |  |  |  |  |  |  |  |  |  |  | 08/12/23 |
| Max. Safe Working Load |  |  |  | 16, 800 kg |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  |  | 22.40 m |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  |  | 10 m |  |  |  | SWL at this radius |  |  |  |  |  | 7, 100 kg |  |  |  |
| Type of lifting gears |  |  |  | Webbing sling |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  |  | 100 kg |  |  |  |  | SWL of lifting gear |  |  |  |  |  | 3ton x 4pcs |  |  |
| Certification of lifting gears |  |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  |  | 06/06/23 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  |  |  |  | Standard hand signals Radio Others______________________ |  |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  |  | Name |  |  |  |  |  |  |  | Qualification / Experience |  |  |  |  |  |  |
| Lifting Supervisor |  |  | Ibrahim / Koh Ban San |  |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |  |  |
| Lorry Crane Operator |  |  | Norhalim / Lim Poh Thiam |  |  |  |  |  |  |  | Qualified crane operator |  |  |  |  |  |  |
| Rigger/Signalman |  |  | Jamari / Ali |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |  |
| Rigger/Signalman |  |  | Rahman / Malik / Hanifah |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |  |
| The lifting Supervisor of this lifting operation is: - Name & Title: Ibrahim / Koh Ban San / Lifting Supervisor - Signature: |  |  |  |  |  |  |  |  |  |  | Steps shall be taken to eliminate danger to personnel involved and others including barriers where appropriate. |  |  |  |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Floor conditions | Is the floor made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Lifting Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations |  |  |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |  |  |
| 1.Deployment of lorry crane at the designated hoisting area |  |  |  |  |  |  |  |  |  | Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 2.Hoist up platform to 3rd floor swing gate opening |  |  |  |  |  |  |  |  |  | Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 3.Secured platform onto building railing/pillar with strapping belt |  |  |  |  |  |  |  |  |  | Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 4.Shift oven into platform |  |  |  |  |  |  |  |  |  | Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 5.Secured oven onto platform with strapping belt |  |  |  |  |  |  |  |  |  | Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 6.Hoist down oven together with platform to the ground |  |  |  |  |  |  |  |  |  | Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 7.Load onto lorry chassis |  |  |  |  |  |  |  |  |  | Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 8.Transport to another location |  |  |  |  |  |  |  |  |  | Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 9.Job complete |  |  |  |  |  |  |  |  |  | Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| - Sketch of Zone of Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Refer to attached |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Name: Zailani |  |  |  |  | Signature: |  |  |  |  |  |  | Date: 18/02/23 |  |  |  |  |  |
| Prepared by: Name: Ibrahim |  |  |  |  | Signature: |  |  |  |  |  |  | Date: 18/02/23 |  |  |  |  |  |
| Assessed by: Name: Kevin Wong |  |  |  |  | Signature: |  |  |  |  |  |  | Date: 18/02/23 |  |  |  |  |  |
| Approved by: Name: Eric Wong |  |  |  |  | Signature: |  |  |  |  |  |  | Date: 18/02/23 |  |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |