| EWMTPL | PTW-LIFTING PLAN | LP/PTW-01 |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 05/12/22 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project: |  | Hoist down machine form lorry chassis, shift and position to location |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation: |  | 23 Loyang Way – GE Aviation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of lifting operation: |  | 13/12/22 |  |  |  | Time of lifting operation: 09:45 am |  |  |  |  |  |  |  |  |  |
| Validity period of lifting operation: |  | 1 day |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | Tigo 1414/1415 - Odv machine |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  | 170 x 155 x 255 cm |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 1, 100 kg |  |  |  | Known weight |  |  |  |  | Estimated weight |  |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  |  |  |  | Determined by drawing |  |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Lorry crane |  |  |  |  |  |  | Mobile crane |  |  |  |  |  |
| LM/LE Registration No. |  |  | LM 093791C |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 22/01/22 |  | Expiry date of certificate |  |  |  |  |  |  |  |  |  | 20/04/23 |
| Max. Safe Working Load |  |  | 9, 440 kg |  |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 16.40 m |  |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 8 m |  |  |  | SWL at this radius |  |  |  |  | 5, 200 kg |  |  |  |
| Type of lifting gears |  |  | Webbing sling |  |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 50 kg |  |  | SWL of lifting gear |  |  |  |  |  |  | 3ton |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 06/06/23 |  |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others _____________________________ |  |  |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  |  | Qualification / Experience |  |  |  |  |  |
| Site Supervisor |  | Ibrahim / Zahari |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Ibrahim / Zahari |  |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |  |
| Lifting Equipment Operator |  | Ngamin/ Lim Boon Lay / Norhalim |  |  |  |  |  |  |  | Qualified crane operator |  |  |  |  |  |
| Rigger/Signalman |  | Rahman / Ali / Samad / Ahmad |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| Rigger/Signalman |  | Jamari / Malik / Hanifah |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| The lifting supervisor of this operation is: Name : Ibrahim / Zahari / Koh Ban San Signature: |  |  |  |  |  |  |  |  |  | Steps shall be taken to eliminate danger to personnel involved and others including barriers where appropriate. |  |  |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |  |  |
| 1.Deploy lorry loader at designated unloading bay |  |  |  |  |  |  |  | Zahari / Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 2.Hoist down case from lorry chassis to the ground |  |  |  |  |  |  |  | Zahari / Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 3.Uncrate case |  |  |  |  |  |  |  | Zahari / Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 4.Hoist up and detach machine from base |  |  |  |  |  |  |  | Zahari / Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 5.Swing crane away from base |  |  |  |  |  |  |  | Zahari / Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 6.Lower down machine to the ground |  |  |  |  |  |  |  | Zahari / Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 7.Insert pallet truck under machine base |  |  |  |  |  |  |  | Zahari / Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 8.Shift and transport machine into factory premise |  |  |  |  |  |  |  | Zahari / Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 9.Position machine at the designated location |  |  |  |  |  |  |  | Zahari / Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 10.Once job complete, team leader will instruct team to perform proper housekeeping |  |  |  |  |  |  |  | Zahari / Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 11.All debris will be clear and disposed |  |  |  |  |  |  |  | Zahari / Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| 12.Job complete |  |  |  |  |  |  |  | Zahari / Ibrahim / Koh Ban San |  |  |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  |  | Signature: |  |  |  |  | Date: 13/12/22 |  |  |  |  |  |  |
| Prepared by: Zahari Designation: Lifting Supervisor |  |  |  | Signature: |  |  |  |  | Date: 13/12/22 |  |  |  |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  |  | Signature: |  |  |  |  | Date: 13/12/22 |  |  |  |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  |  | Signature: |  |  |  |  | Date: 13/12/22 |  |  |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |