| EWMTPL | PTW-LIFTING PLAN | LP/PTW-01 |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 08/10/2020 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project: |  | Unloading/hoisting machine |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation: |  | 273 Jalan Ahmad Ibrahim – Baker Hughes (S) Pte |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of lifting operation: |  | Est: 17/10/2020 |  |  |  | Time of lifting operation: 09:45 am |  |  |  |  |  |  |  |  |  |
| Validity period of lifting operation: |  | Est: 2 day |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | McCoy Torque machine |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  | 650 x 243 x 307 cm |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: Gross Wt |  | 14, 254 kg |  |  |  | Known weight |  |  |  |  | Estimated weight |  |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  |  |  |  | Determined by drawing |  |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Lorry crane |  |  |  |  |  |  | Mobile crane |  |  |  |  |  |
| LM/LE Registration No. |  |  | LM474127P |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 25/02/2020 |  | Expiry date of certificate |  |  |  |  |  |  |  |  |  | 24/02/2021 |
| Max. Safe Working Load |  |  | 32, 500 kg |  |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 43.00 m |  |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | m |  |  |  | SWL at this radius |  |  |  |  | kg |  |  |  |
| Type of lifting gears |  |  | Wire/webbing sling/shackle |  |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | kg |  |  | SWL of lifting gear |  |  |  |  |  |  |  |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others _____________________________ |  |  |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  |  | Qualification / Experience |  |  |  |  |  |
| Site Supervisor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  |  |  |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |  |
| Lifting Equipment Operator |  |  |  |  |  |  |  |  |  | Qualified crane operator |  |  |  |  |  |
| Rigger/Signalman |  |  |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| Rigger/Signalman |  |  |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| The lifting supervisor of this operation is: Name & Title: Wong Yen Siong / Zahari / Lifting Supervisor Signature: |  |  |  |  |  |  |  |  |  | Steps shall be taken to eliminate danger to personnel involved and others including barriers where appropriate. Tools box meeting to take place and lifting plan be communicated |  |  |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Lifting Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |  |  |
| 1.Deploy mobile crane at designated unloading bay |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 2.Hoist down cases from container to the ground |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 3.Uncrate case |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 4.Hoist up and detach machine from base |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 5.Swing crane and lower down machine to near ground level |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 6.Insert rollers/pallet truck under machine base |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 7.Shift and transport machine into production area at ground floor |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 8.Position machine at the designated location |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 9.Unload machine from rollers and insert levelling pad under machine bed |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 10.Once job complete, team leader will instruct team to perform proper housekeeping, all debris will be clear and disposed |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 11.All debris will be clear and disposed |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 12.Job complete |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| - Sketch of Zone of Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sketch of the initial pick-up location, load path and lay-down area (include any obstructions or equipment clashes that may occur and how they will be avoided) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  |  | Signature: |  |  |  |  | Date: 17/10/2020 |  |  |  |  |  |  |
| Prepared by: Wong Yen Siong Designation: Lifting Supervisor |  |  |  | Signature: |  |  |  |  | Date: 17/10/2020 |  |  |  |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  |  | Signature: |  |  |  |  | Date: 17/10/2020 |  |  |  |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  |  | Signature: |  |  |  |  | Date: 17/10/2020 |  |  |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |