| Eric Wong Machinery Transportation Pte Ltd | Lifting Plan / Permit to Work | LP/PTW-01 |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 13/01/23 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  | Unloading/hoisting of machine |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation |  | 12 Tukang Innovation Drive – Dormakaba Production GMBH & CO.KG |  |  |  |  |  |  |  |  |  |  |  |
| Date/time of lifting operation |  | 30/01/23 – 09:45 am |  |  |  |  |  |  |  |  |  |  |  |
| Validity period of lifting operation |  | 1 day |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads to be Hoist |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | Mazak VCP-400L Vertical Machining Center |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  | 3100 x 1700 x 2520 mm |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 5, 020 kgs |  |  |  | Known weight |  |  | Estimated weight |  |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  |  | Determined by drawing |  |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Mobile crane |  |  |  |  |  | Lorry loader |  |  |  |  |
| LM/LE Registration No. |  |  | LM 961229B |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 17/09/22 |  | Expiry date of certificate |  |  |  |  |  |  |  | 13/09/23 |
| Max. Safe Working Load |  |  | 20, 100 kg |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 21.90 m |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 6 m |  |  |  | SWL at this radius |  |  | 14, 300 kg |  |  |  |
| Type of lifting gears |  |  | Wire sling |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 60 kg |  |  | SWL of lifting gear |  |  |  |  | 4ton x 4pcs |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 27/11/23 |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  | Qualification / Experience |  |  |  |  |
| Site Supervisor |  | Koh Ban San / Wong Yen Siong |  |  |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Koh Ban San / Wong Yen Siong |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |
| Lifting Equipment Operator |  | Norhalim/Lim Poh Thiam/Lim Poh Soon |  |  |  |  |  |  | Qualified crane operator |  |  |  |  |
| Rigger/Signalman |  | Ali / Malik / Sing Kwok Liang / Rahman |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |
| Rigger/Signalman |  | Hanifah / Jamari / Ahmad / Ibrahim |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Lifting Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |
| 1.Deploy lorry loader at designated unloading area |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |
| 2.Hoist down case from lorry chassis to the ground |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |
| 3.Uncrate case and put aside |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |
| 4.Insert sling to crane hook and secure to rigging point of machine |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |
| 5.Hoist up and detach machine from base |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |
| 6.Load back machine onto lorry chassis |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |
| 7.Reverse lorry to loading bay |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8.Jack up machine and insert rollers under machine bed |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |
| 9.Shift and transport machine into factory premise at ground floor |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |
| 10.Position machine at the designated location |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |
| 11.Unload machine from rollers and insert levelling pad under machine bed |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |
| 12.Once job complete, proper housekeeping will be done |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |
| 13.All debris will be clear and dispose |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |
| 14.Job complete |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  |  | Signature: |  |  |  | Date: 30/01/23 |  |  |  |  |  |
| Prepared by: Koh Ban San Designation: Lifting Supervisor |  |  |  | Signature: |  |  |  | Date: 30/01/23 |  |  |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  |  | Signature: |  |  |  | Date: 30/01/23 |  |  |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  |  | Signature: |  |  |  | Date: 30/01/23 |  |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work |  |  |  |  |  |  |  |  |  |  |  |  |  |