| Eric Wong Machinery Transportation PL | PTW-LIFTING PLAN | LP- MS-01 |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 23/11/2021 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project: |  | Hoist up 1 unit machine to 2nd floor using platform & mobile crane |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation: |  | 10 Calshot Rd – SAESL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of lifting operation: |  | 02/12/21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Time of operation: |  | 09:40 am |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Duration of operation |  | 1 day |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  |  | Global S Blue 12.22.10 CMM |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimensions of load: |  |  | 1898 x 3605 x 3488 mm |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  |  | 5, 750 kg |  |  |  |  |  | Known weight |  |  | Estimated weight |  |  |  |  |
| Centre of gravity: |  |  | Obvious |  |  |  |  |  | Estimated |  |  | Determined by drawing |  |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  |  |  | Lorry crane |  |  |  |  | Mobile crane |  |  |  |  |  |  |
| LM/LE Registration No. |  |  |  |  | LM474127P |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  |  |  | 15/12/20 |  | Expiry date of certificate |  |  |  |  |  |  |  |  | 14/12/21 |
| Max. Safe Working Load |  |  |  |  | 32, 500 kg |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  |  |  | 43.00 m |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  |  |  | 6.5 m |  |  | SWL at this radius |  |  |  |  | 17, 500 kg |  |  |  |
| Type of lifting gears |  |  |  |  | Wire/webbing sling, shackle |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  |  |  | 3, 500 kg |  |  |  | SWL of lifting gear |  |  |  |  | 4 ton x 4pcs |  |  |
| Certification of lifting gears |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  |  |  | 13/01/22 |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  |  |  | Name |  |  |  |  |  | Qualification / Experience |  |  |  |  |  |  |
| Lifting Supervisor |  |  |  | Zahari / Koh Ban San |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |  |  |
| Lifting Equipment Operator |  |  |  | Yeo Hock Cheng / Loh Hock Guan |  |  |  |  |  | Qualified crane operator |  |  |  |  |  |  |
| Rigger/Signalman |  |  |  | Malik / Hanifah / Ahmad |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |  |
| Rigger/Signalman |  |  |  | Sing Kwok Liang / Ali / Asfandi |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |  |
| The lifting Supervisor of this lifting operation is: - Name & Title: Zahari / Koh Ban San / Lifting Supervisor - Signature: |  |  |  |  |  |  |  |  |  | Steps shall be taken to eliminate danger to personnel involved and others including barriers where appropriate. |  |  |  |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Floor conditions | Is the floor made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Lifting Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations |  |  |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |  |
| 1.Deploy mobile/lorry crane at the designated hoisting area |  |  |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |
| 2.Load machine onto platform |  |  |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |
| 3.Secure machine onto platform with strapping belt |  |  |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |
| 4.Hoist up platform together with machine to 2nd floor shutter door opening |  |  |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |
| 5.Stabilize platform and ensure platform 3ft metal plate protruding is fully lean and rested on door opening |  |  |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |
| 6.Secured front left and right of platform onto building railing/pillar with strapping belt to prevent swing outward |  |  |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |
| 7.Insert pallet truck under machine bed |  |  |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |
| 7.Use of manual pulley to control moving speed of machine when being transport out from platform |  |  |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |
| 8. |  |  |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |
| 9.Shift out machine from scissor platform |  |  |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |
| 10.Transport and position machine at designated location |  |  |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |
| 11.Once job complete, supervisor will instruct team to perform proper housekeeping, all debris will be clear and dispose |  |  |  |  |  |  |  |  |  | Zahari / Koh Ban San |  |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Name: Zailani |  |  |  |  |  | Signature: |  |  |  |  | Date: 02/12/21 |  |  |  |  |  |
| Prepared by: Name: Zahari |  |  |  |  |  | Signature: |  |  |  |  | Date: 02/12/21 |  |  |  |  |  |
| Assessed by: Name: Kevin Wong |  |  |  |  |  | Signature: |  |  |  |  | Date: 02/12/21 |  |  |  |  |  |
| Approved by: Name: Eric Wong |  |  |  |  |  | Signature: |  |  |  |  | Date: 02/12/21 |  |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |