| EWMTPL | PTW-LIFTING PLAN | LP/PTW-01 |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 01/09/21 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project: |  | Unloading/hoisting machine |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation: |  | 18 Joo Koon Circle – Yamazaki Mazak |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of lifting operation: |  | 02/09/21 |  |  |  | Time of lifting operation: 09:45 am |  |  |  |  |  |  |  |  |  |
| Validity period of lifting operation: |  | 1 day |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | Laser Processing machine / OPTIREX 3015DDL |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  | 670 X 307 X 251 cm |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 11, 325 kgs |  |  |  | Known weight |  |  |  |  | Estimated weight |  |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  |  |  |  | Determined by drawing |  |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Lorry crane |  |  |  |  |  |  | Mobile crane |  |  |  |  |  |
| LM/LE Registration No. |  |  | LM 084683X |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 19/07/21 |  | Expiry date of certificate |  |  |  |  |  |  |  |  |  | 18/07/22 |
| Max. Safe Working Load |  |  | 17, 840 kg |  |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 17.30 m |  |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 5.6 m |  |  |  | SWL at this radius |  |  |  |  | 14, 530 kg |  |  |  |
| Type of lifting gears |  |  | Wire sling, shackle |  |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 100 kg |  |  | SWL of lifting gear |  |  |  |  |  |  | 4ton x 4 pcs |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 09/12/21 |  |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |  |
| What are the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others _____________________________ |  |  |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  |  | Qualification / Experience |  |  |  |  |  |
| Site Supervisor |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |  |
| Lifting Equipment Operator |  | Lim Poh Thiam / Norhalim |  |  |  |  |  |  |  | Qualified crane operator |  |  |  |  |  |
| Rigger/Signalman |  | Ali / Sing Kwok Liang / Ahmad |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| Rigger/Signalman |  | Hanifah / Malik / Asfandi / |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| The lifting supervisor of this operation is: Name & Title: Wong Yen Siong / Zahari / Lifting Supervisor Signature: |  |  |  |  |  |  |  |  |  | Steps shall be taken to eliminate danger to personnel involved and others including barriers where appropriate |  |  |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Lifting Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |  |  |
| 1.Deploy lorry crane at designated unloading area |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 2.Uncrate case |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 3.Hoist up and detach machine from base |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 4.Swing crane to unloading area |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 5.Lower down machine to near ground level |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 6.Insert rollers under machine base |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 7.Shift and transport machine into production area |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 8.Position machine at the designated location |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 9.Unload machine from rollers and insert levelling pad under machine bed |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 10.Once job complete, team leader will instruct team to perform proper housekeeping |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| 11.All debris will be clear and disposed |  |  |  |  |  |  |  | Wong Yen Siong / Zahari |  |  |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  |  | Signature: |  |  |  |  | Date: 02/09/2021 |  |  |  |  |  |  |
| Prepared by: Wong Yen Siong Designation: Lifting Supervisor |  |  |  | Signature: |  |  |  |  | Date: 02/09/2021 |  |  |  |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  |  | Signature: |  |  |  |  | Date: 02/09/2021 |  |  |  |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  |  | Signature: |  |  |  |  | Date: 02/09/2021 |  |  |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |