| EWMTPL | PTW-LIFTING PLAN | LP/PTW-01 |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 12/11/21 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project: |  | Unloading/hoisting machine |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation: |  | 3 Joo Koon Circle – AME International Pte Ltd |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of lifting operation: |  | 15-16/11/21 |  |  |  | Time of lifting operation: 09:45 am |  |  |  |  |  |  |  |  |  |
| Validity period of lifting operation: |  | 1-2 day |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | Kuraki CNC Horizontal Boring |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  | 469 x 271 x 196 cm |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 10, 000 kgs |  |  |  | Known weight |  |  |  |  | Estimated weight |  |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  |  |  |  | Determined by drawing |  |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Lorry crane |  |  |  |  |  |  | Mobile crane |  |  |  |  |  |
| LM/LE Registration No. |  |  | LM 077126C |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 24/05/21 |  | Expiry date of certificate |  |  |  |  |  |  |  |  |  | 23/05/22 |
| Max. Safe Working Load |  |  | 18, 240 kg |  |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 15.20 m |  |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 5.6 m |  |  |  | SWL at this radius |  |  |  |  | 14, 800 kg |  |  |  |
| Type of lifting gears |  |  | Wire sling, shackle |  |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 100 kg |  |  | SWL of lifting gear |  |  |  |  |  |  | 4 ton x 4pcs |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 14/12/21 |  |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |  |
| What are the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others _____________________________ |  |  |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  |  | Qualification / Experience |  |  |  |  |  |
| Site Supervisor |  | Koh Ban San / Wong Yen Siong |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Koh Ban San / Wong Yen Siong |  |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |  |
| Lifting Equipment Operator |  | Lim Poh Soon / Lim Poh Thiam |  |  |  |  |  |  |  | Qualified crane operator |  |  |  |  |  |
| Rigger/Signalman |  | Ali / Malik / Asfandi |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| Rigger/Signalman |  | Ahmad / Sing Kwok Liang / Hanifah |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| The lifting supervisor of this operation is: Name & Title: Koh Ban San / Wong Yen Siong / Lifting Supervisor Signature: |  |  |  |  |  |  |  |  |  | Steps shall be taken to eliminate danger to personnel involved and others including barriers where appropriate. |  |  |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Lifting Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |  |  |
| 1.Deploy lorry crane at designated unloading area |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong |  |  |  |  |  |  |  |
| 2.Hoist down case from container to the ground |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong |  |  |  |  |  |  |  |
| 3.Uncrate case |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong |  |  |  |  |  |  |  |
| 4.Hoist up and detach machine from base |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong |  |  |  |  |  |  |  |
| 5. Load machine onto lorry chassis |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong |  |  |  |  |  |  |  |
| 6.Transport machine into inside factory |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong |  |  |  |  |  |  |  |
| 7.Using factory overhead crane to unload machine |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong |  |  |  |  |  |  |  |
| 8.Position machine at the designated location |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong |  |  |  |  |  |  |  |
| 9.Once job complete, team leader will instruct team to perform proper housekeeping |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong |  |  |  |  |  |  |  |
| 10.All debris will be clear and disposed |  |  |  |  |  |  |  | Koh Ban San / Wong Yen Siong |  |  |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  |  | Signature: |  |  |  |  | Date: 15-16/11/2021 |  |  |  |  |  |  |
| Prepared by: Wong Yen Siong Designation: Lifting Supervisor |  |  |  | Signature: |  |  |  |  | Date: 15-16/11/2021 |  |  |  |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  |  | Signature: |  |  |  |  | Date: 15-16/11/2021 |  |  |  |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  |  | Signature: |  |  |  |  | Date: 15-16/11/2021 |  |  |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |