| Eric Wong Machinery Transportation Pte Ltd | Lifting Plan / Permit to Work | LP/PTW-00 |  |
| --- | --- | --- | --- |
|  |  | Rev: 00 | Date: 05/06/25 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  | Hoist up 1 unit machine to 3rd floor by using platform and mobile crane |  |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation |  | Blk 1 Bulim Square #03-52 – Meridionale Impianti Singapore Pte Ltd |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of lifting operation |  | 12/06/25 |  |  |  |  |  | Time of lifting operation: 10:00 am |  |  |  |  |  |  |
| Validity period of lifting operation |  | 1 day |  |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads to be Hoist |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | CNC Milling machine |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  | 210 x 185 x 240 cm |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 5, 000 kg |  |  |  | Known weight |  |  | Estimated weight |  |  |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  |  | Determined by drawing |  |  |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Mobile crane |  |  |  |  |  |  | Lorry loader |  |  |  |  |
| LM/LE Registration No. |  |  | LM474927J |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 09/01/25 |  | Expiry date of certificate |  |  |  |  |  |  |  |  | 07/01/26 |
| Max. Safe Working Load |  |  | 25, 300 kg |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 25.2 m |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 12m |  |  |  | SWL at this radius |  |  |  | 10, 000 kg |  |  |  |
| Type of lifting gears |  |  | Wire sling, shackle |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 60 kg |  |  | SWL of lifting gear |  |  |  |  |  | 4ton x 4pcs |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 15/10/25 |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  |  | Qualification / Experience |  |  |  |  |
| Site Supervisor |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |
| Lifting Equipment Operator |  | Loh Hock Guan / Peh Chin Lee / Lim Poh Thiam / Lim Poh Son / Norhalim |  |  |  |  |  |  |  | Qualified crane operator |  |  |  |  |
| Rigger/Signalman |  | Rahman / Ahmad / Malik / Sarawanan / Vignesh |  |  |  |  |  |  |  | Qualified rigger/ signalman |  |  |  |  |
| Rigger/Signalman |  | Ibrahim / Sing Kwok Liang / Hanifah / Aziz / Rizal |  |  |  |  |  |  |  | Qualified rigger/ signalman |  |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operatio4n been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |
| 1.Deploy 2 x mobile crane at designated hoisting area |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Zahari / Koh Ban San / Ibrahim |  |  |  |  |
| 2.Set up crane with outrigger fully extended and resting on steel plate/timber mats as base plate |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Zahari / Koh Ban San / Ibrahim |  |  |  |  |
| 31 x mobile crane to hoist up platform to 3RD floor shutter gate opening |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Zahari / Koh Ban San / Ibrahim |  |  |  |  |
| 4.Stabilize platform effectively and ensure platform 3ft metal protruding is fully lean and rested on the opening slab |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Zahari / Koh Ban San / Ibrahim |  |  |  |  |
| 5.Tied back platform to competent point and secured using 1 x 30ton mobile crane |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Zahari / Koh Ban San / Ibrahim |  |  |  |  |
| 6.Use strong belt to secure front left and right of platform onto building railing/pillar to prevent swing outward |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Zahari / Koh Ban San / Ibrahim |  |  |  |  |
| 7.Rigger to insert sling to crane hook and secured to machine rigging point |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Zahari / Koh Ban San / Ibrahim |  |  |  |  |
| 8.1 x 50ton mobile crane to hoist up machine to 3rd floor |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Zahari / Koh Ban San / Ibrahim |  |  |  |  |
| 9.Lower down machine onto platform |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Zahari / Koh Ban San / Ibrahim |  |  |  |  |
| 10.Insert rollers under machine bed |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Zahari / Koh Ban San / Ibrahim |  |  |  |  |
| 11.Shift out machine from platform and position at the designated location |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Zahari / Koh Ban San / Ibrahim |  |  |  |  |
| 12.Once job complete, team leader will instruct the team to perform proper housekeeping |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Zahari / Koh Ban San / Ibrahim |  |  |  |  |
| 13.All debris will be clear and dispose |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Zahari / Koh Ban San / Ibrahim |  |  |  |  |
| 14.Job complete |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Zahari / Koh Ban San / Ibrahim |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  |  | Signature: |  |  |  |  |  | Date: 05/06/25 |  |  |  |  |
| Prepared by: Wong Yen Siong Designation: Lifting Supervisor |  |  |  | Signature: |  |  |  |  |  | Date: 05/06/25 |  |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  |  | Signature: |  |  |  |  |  | Date: 05/06/25 |  |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  |  | Signature: |  |  |  |  |  | Date: 05/06/25 |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |