| Eric Wong Machinery Transportation Pte Ltd | Lifting Plan / Permit to Work | LP/PTW-00 |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 21/11/24 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  | To hoist 1 machine to 4th floor by using platform and lorry crane |  |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation |  | Blk 31 Defu Lane 10 #04-72 (Alcotec Precision Engineering Pte Ltd) |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of lifting operation |  | 06/12/24 |  |  |  |  |  | Time of lifting operation: 10:00 am |  |  |  |  |  |  |
| Validity period of lifting operation |  | 1 day job |  |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads to be Hoist |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | 1 unit PFG-CL3060AH Grinder |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  | 265 x 155 x 180 cm |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 1, 700 kg |  |  |  | Known weight |  |  | Estimated weight |  |  |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  |  | Determined by drawing |  |  |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Mobile crane |  |  |  |  |  |  | Lorry loader |  |  |  |  |
| LM/LE Registration No. |  |  | LM961229B |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 17/07/24 |  | Expiry date of certificate |  |  |  |  |  |  |  |  | 16/07/25 |
| Max. Safe Working Load |  |  | 20, 100 kg |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 21.90 m |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 13.4 m |  |  |  | SWL at this radius |  |  |  | 5, 500 kg |  |  |  |
| Type of lifting gears |  |  | Wire sling, shackle |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 60 kg |  |  | SWL of lifting gear |  |  |  |  |  | 4ton x 4pcs |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 15/10/25 |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  |  | Qualification / Experience |  |  |  |  |
| Site Supervisor |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |
| Lifting Equipment Operator |  | Lim Poh Soon / Lim Poh Thiam / Norhalim |  |  |  |  |  |  |  | Qualified crane operator |  |  |  |  |
| Rigger/Signalman |  | Malik / Ahmad / Aziz / Sarawanan / Rahman |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |
| Rigger/Signalman |  | Sing Kwok Liang / Hanifah / Rizal / Vignesh |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |
| 1.Deploy 2 x lorry crane at designated hoisting area |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |
| 2.1 x lorry crane to hoist up platform to 4th floor wall hacking opening |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |
| 3.Stabilize platform effectively and ensure platform 3ft metal protruding is fully lean and rested on the opening slab |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |
| 4.Tied back platform to competent point and secured using 1 x lorry crane |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |
| 5.Use strong belt to secure front left and right of platform onto building railing/pillar to prevent swing outward |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |
| 6.Riggers to insert sling to crane hook |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |
| 7.Secured sling to machine rigging point |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |
| 8.To hoist up machine to 4th floor |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |
| 9.Lower down machine onto platform |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |
| 10.Insert pallet truck under machine bed |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |
| 11.Shift out from platform and position into tenant premise |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |
| 12.Once job complete, team leader will instruct the team to perform proper housekeeping |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |
| 13.All debris will be clear and dispose |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |
| 14.Job complete |  |  |  |  |  |  |  |  |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  |  | Signature: |  |  |  |  |  | Date: 06/12/24 |  |  |  |  |
| Prepared by: Wong Yen Siong Designation: Lifting Supervisor |  |  |  | Signature: |  |  |  |  |  | Date: 06/12/24 |  |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  |  | Signature: |  |  |  |  |  | Date: 06/12/24 |  |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  |  | Signature: |  |  |  |  |  | Date: 06/12/24 |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |