| Eric Wong Machinery Transportation Pte Ltd | Lifting Plan / Permit to Work | LP/PTW |  |
| --- | --- | --- | --- |
|  |  | Rev: 00 | Date: 05/12/25 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  | Shift out and hoist up machine onto Malaysia lorry |  |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation |  | #### 26 A.M.K Ind Pk 2 - Meiban Mold Manufacture Pte Ltd |  |  |  |  |  |  |  |  |  |  |  |  |
| Date/time of lifting operation |  | 16/12/25 – 09:30 am |  |  |  |  |  |  |  |  |  |  |  |  |
| Validity period of lifting operation |  | 1 day |  |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads to be Hoist |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | Creator CR-6C |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  | 290 x 185 x 285 cm |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 5, 000 kg |  |  |  | Known weight |  |  |  |  |  | Estimated weight |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  |  |  |  |  | Determined by drawing |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Lorry crane |  |  |  |  |  |  |  |  | Mobile crane |  |  |
| LM/LE Registration No. |  |  | LM406824P |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 23/08/25 |  | Expiry date of certificate |  |  |  |  |  |  |  |  | 22/08/26 |
| Max. Safe Working Load |  |  | 16, 800 kg |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 22.40 m |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 6m |  |  |  | SWL at this radius |  |  | 12, 200 kg |  |  |  |  |
| Type of lifting gears |  |  | Wire sling, shackle |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 50 kg |  |  | SWL of lifting gear |  |  |  |  | 4ton x 4pcs |  |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 16/11/26 |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  |  |  |  | Qualification / Experience |  |  |
| Site Supervisor |  | Zahari / Ibrahim / Zaharin / Wong Yen Siong |  |  |  |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Zahari / Ibrahim / Zaharin / Wong Yen Siong |  |  |  |  |  |  |  |  |  | Qualified lifting supervisor |  |  |
| Lifting Equipment Operator |  | Lim Poh Thiam / Ngaimin / Norhalim / Azmi |  |  |  |  |  |  |  |  |  | Qualified crane operator |  |  |
| Rigger/Signalman |  | Malik / Rahman / Jamari / Sing Kwok Liang |  |  |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |
| Rigger/Signalman |  | Hanifah / Aziz / Ahmad / Kughanesswaran |  |  |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Lifting Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |  |
| 1.Deploy lorry loader at designated hoisting area |  |  |  |  |  |  |  | Zahari / Ibrahim / Wong Yen Siong |  |  |  |  |  |  |
| 2.Set up crane with outrigger fully extended and resting on timber mats as base plate |  |  |  |  |  |  |  | Zahari / Ibrahim / Wong Yen Siong |  |  |  |  |  |  |
| 3.Shift out machine from production to loading area |  |  |  |  |  |  |  | Zahari / Ibrahim / Wong Yen Siong |  |  |  |  |  |  |
| 4.Rigger to insert sling to crane hook |  |  |  |  |  |  |  | Zahari / Ibrahim / Wong Yen Siong |  |  |  |  |  |  |
| 5.Secured sling to rigging point of machine |  |  |  |  |  |  |  | Zahari / Ibrahim / Wong Yen Siong |  |  |  |  |  |  |
| 6.Hoist up machine and load up onto Malaysia lorry |  |  |  |  |  |  |  | Zahari / Ibrahim / Wong Yen Siong |  |  |  |  |  |  |
| 7.Malaysia driver to secured machine with strapping belt |  |  |  |  |  |  |  | Zahari / Ibrahim / Wong Yen Siong |  |  |  |  |  |  |
| 8.Transport out of customer premise |  |  |  |  |  |  |  | Zahari / Ibrahim / Wong Yen Siong |  |  |  |  |  |  |
| 9.Once job complete, proper housekeeping will be done |  |  |  |  |  |  |  | Zahari / Ibrahim / Wong Yen Siong |  |  |  |  |  |  |
| 10.All debris will be clear and disposed |  |  |  |  |  |  |  | Zahari / Ibrahim / Wong Yen Siong |  |  |  |  |  |  |
| 11.Job complete |  |  |  |  |  |  |  | Zahari / Ibrahim / Wong Yen Siong |  |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  |  | Signature: |  |  |  |  | Date: 05/12/25 |  |  |  |  |  |
| Prepared by: Zahari Designation: Lifting Supervisor |  |  |  | Signature: |  |  |  |  | Date: 05/12/25 |  |  |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  |  | Signature: |  |  |  |  | Date: 05/12/25 |  |  |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  |  | Signature: |  |  |  |  | Date: 05/12/25 |  |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |