| Eric Wong Machinery Transportation Pte Ltd | Lifting Plan / Permit to Work | LP/PTW |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 15/05/25 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  | To hoist down machine from 2nd floor through wall hacking opening by using platform and lorry crane |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation |  | Blk 9002 Tampines St 93 #02-02 (Jian He Precision Engineering Pte Ltd) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of lifting operation |  | 24/05/25 (Saturday) |  |  |  |  |  | Time of lifting operation: 09:45 am |  |  |  |  |  |  |  |
| Validity period of lifting operation |  | 1 day |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads to be Hoist |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | Sodick AQ400L |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  | 1920 x 2616 x 2095 mm |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 4, 300 kg |  |  |  | Known weight |  |  |  | Estimated weight |  |  |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  |  |  | Determined by drawing |  |  |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Mobile crane |  |  |  |  |  |  |  | Lorry loader |  |  |  |  |
| LM/LE Registration No. |  |  | LM474927J |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 09/01/25 |  | Expiry date of certificate |  |  |  |  |  |  |  |  |  | 07/01/26 |
| Max. Safe Working Load |  |  | 25, 300 kg |  |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 31.1m |  |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 10 m |  |  |  | SWL at this radius |  |  |  |  | 13, 500 kg |  |  |  |
| Type of lifting gears |  |  | Wire sling, shackle |  |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 50 kg |  |  | SWL of lifting gear |  |  |  |  |  |  | 4ton x 4pcs |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 26/11/25 |  |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  |  |  | Qualification / Experience |  |  |  |  |
| Site Supervisor |  | Wong Yen Siong / Zahari / Koh Ban San / Ibrahim |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Wong Yen Siong / Zahari / Koh Ban San / Ibrahim |  |  |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |
| Lifting Equipment Operator |  | Loh Hock Guan / Lim Poh Soon / Norhalim / Lim Poh Thiam |  |  |  |  |  |  |  |  | Qualified crane operator |  |  |  |  |
| Rigger/Signalman |  | Sing Kwok Liang / Hanifah / Aziz / Vignesh / Rizal |  |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |
| Rigger/Signalman |  | Ahmad / Rahman / Kughanesswaran / Malik |  |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |  |
| 1.Deploy mobile/lorry crane at designated hoisting area |  |  |  |  |  |  |  |  | Wong Yen Siong/Zahari/Koh Ban San |  |  |  |  |  |  |
| 2.Hoist up platform to 3rd floor wall hacking opening |  |  |  |  |  |  |  |  | Wong Yen Siong/Zahari/Koh Ban San |  |  |  |  |  |  |
| 3.Stabilize platform effectively and ensure platform 3ft metal protruding is fully lean and rested on the opening slab |  |  |  |  |  |  |  |  | Wong Yen Siong/Zahari/Koh Ban San |  |  |  |  |  |  |
| 4.Tied back platform to competent point and secured using 1 x lorry crane |  |  |  |  |  |  |  |  | Wong Yen Siong/Zahari/Koh Ban San |  |  |  |  |  |  |
| 5.Use strong belt to secure front left and right of platform onto building railing/pillar to prevent swing outward |  |  |  |  |  |  |  |  | Wong Yen Siong/Zahari/Koh Ban San |  |  |  |  |  |  |
| 6.Shift out machine from production into platform |  |  |  |  |  |  |  |  | Wong Yen Siong/Zahari/Koh Ban San |  |  |  |  |  |  |
| 7.Insert sling to crane hook and secure onto rigging point of machine |  |  |  |  |  |  |  |  | Wong Yen Siong/Zahari/Koh Ban San |  |  |  |  |  |  |
| 8.Mobile crane to hoist down machine to the ground |  |  |  |  |  |  |  |  | Wong Yen Siong/Zahari/Koh Ban San |  |  |  |  |  |  |
| 9.Load machine onto lorry chassis and secure with strapping belt |  |  |  |  |  |  |  |  | Wong Yen Siong/Zahari/Koh Ban San |  |  |  |  |  |  |
| 10.Deliver machine to new location |  |  |  |  |  |  |  |  | Wong Yen Siong/Zahari/Koh Ban San |  |  |  |  |  |  |
| 11.Once job complete, team leader will instruct the team to perform proper housekeeping |  |  |  |  |  |  |  |  | Wong Yen Siong/Zahari/Koh Ban San |  |  |  |  |  |  |
| 12.All debris will be clear and dispose |  |  |  |  |  |  |  |  | Wong Yen Siong/Zahari/Koh Ban San |  |  |  |  |  |  |
| 13.Job complete |  |  |  |  |  |  |  |  | Wong Yen Siong/Zahari/Koh Ban San |  |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  |  | Signature: |  |  |  |  | Date: 15/05/25 |  |  |  |  |  |  |
| Prepared by: Wong Yen Siong Designation: Lifting Supervisor |  |  |  | Signature: |  |  |  |  | Date: 15/05/25 |  |  |  |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  |  | Signature: |  |  |  |  | Date: 15/05/25 |  |  |  |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  |  | Signature: |  |  |  |  | Date: 15/05/25 |  |  |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |