| Eric Wong Machinery Transportation Pte Ltd | Lifting Plan / Permit to Work | LP/PTW-00 |  |
| --- | --- | --- | --- |
|  |  | Rev: 00 | Date: 26/09/25 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  | Hoisting up bar feeder at 6th floor through swing gate opening by using platform & mobile crane |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation |  | 10 Tampines North Dr #06-08 Turntech Precision Engineering Pte Ltd |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of lifting operation |  | 07/10/25 |  |  |  |  |  | Time of lifting operation |  |  |  |  |  |  | 10:00 am |
| Validity period of lifting operation |  | 1 day |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads to be Hoist |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | Bar Feeder |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  | 400 x 60 x 120 cm |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 300 kg each |  |  | Known weight |  |  |  | Estimated weight |  |  |  |  |  |  |
| Centre of gravity: |  | Obvious |  |  | Estimated |  |  |  | Determined by drawing |  |  |  |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | 601 mobile crane |  |  |  |  |  |  |  |  |  |  |  |  |
| LM/LE Registration No. |  |  | LM345825E |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 05/05/25 |  |  |  | Expiry date of certificate |  |  |  |  |  |  | 04/05/26 |  |
| Max. Safe Working Load |  |  | 25, 900 kg |  |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 43 m |  |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 12 m |  |  | SWL at this radius |  |  |  |  | 8, 500 kg |  |  |  |  |
| Safety factor |  |  | 2.93 |  |  | Utilization % |  |  |  |  | 34 % |  |  |  |  |
| Type of lifting gears |  |  | Webbing sling, shackle, platform |  |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 2, 600 kg |  | SWL of lifting gear |  |  |  |  |  |  | 3ton x 4pcs |  |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 05/08/26 |  |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  |  | Qualification / Experience |  |  |  |  |  |
| Site Supervisor |  | Koh Ban San / Zahari / Ibrahim |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Koh Ban San / Zahari / Ibrahim |  |  |  |  |  |  |  | Qualified lifting supervisor |  |  |  |  |  |
| Lifting Equipment Operator |  | Wong Kian Loong / Norhalim / Ngaimin |  |  |  |  |  |  |  | Qualified crane operator |  |  |  |  |  |
| Rigger/Signalman |  | Sing Kwok Liang / Rahman / Malik / Aziz |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| Rigger/Signalman |  | Ahmad / Rizal / Hanifah / Jamari |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |  |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |  |  |
| 1.Deployment of mobile crane at designated hoisting area |  |  |  |  |  |  |  | Ibrahim / Koh Ban San / Zahari |  |  |  |  |  |  |  |
| 2.Set up crane with outrigger fully extended and resting on steel plate/timber mats as base plate |  |  |  |  |  |  |  | Ibrahim / Koh Ban San / Zahari |  |  |  |  |  |  |  |
| 3.Load up bar feeder onto platform and secured with strapping belt |  |  |  |  |  |  |  | Ibrahim / Koh Ban San / Zahari |  |  |  |  |  |  |  |
| 4.Insert sling to crane hook and secure to rigging point of platform |  |  |  |  |  |  |  | Ibrahim / Koh Ban San / Zahari |  |  |  |  |  |  |  |
| 5.Mobile crane to hoist up platform together with bar feeder to 6th floor swing gate opening |  |  |  |  |  |  |  | Ibrahim / Koh Ban San / Zahari |  |  |  |  |  |  |  |
| 6.Stabilize platform effectively and ensure platform 3ft metal protruding is fully lean against and rested on the opening slab |  |  |  |  |  |  |  | Ibrahim / Koh Ban San / Zahari |  |  |  |  |  |  |  |
| 7.Use strong belt to secure front left and right of platform onto building railing/pillar to prevent platform swing outward |  |  |  |  |  |  |  | Ibrahim / Koh Ban San / Zahari |  |  |  |  |  |  |  |
| 8.Insert rollers onto bar feeder stand |  |  |  |  |  |  |  | Ibrahim / Koh Ban San / Zahari |  |  |  |  |  |  |  |
| 9.Shift out from platform and transport into tenant premise |  |  |  |  |  |  |  | Ibrahim / Koh Ban San / Zahari |  |  |  |  |  |  |  |
| 10.Once job complete, team leader will instruct the team to perform proper housekeeping, all debris will be clear and dispose |  |  |  |  |  |  |  | Ibrahim / Koh Ban San / Zahari |  |  |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  |  | Signature: |  |  |  | Date: 26/09/25 |  |  |  |  |  |  |  |
| Prepared by: Ibrahim Designation: Lifting Supervisor |  |  |  | Signature: |  |  |  | Date: 26/09/25 |  |  |  |  |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  |  | Signature: |  |  |  | Date: 26/09/25 |  |  |  |  |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  |  | Signature: |  |  |  | Date: 26/09/25 |  |  |  |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |