| Eric Wong Machinery Transportation Pte Ltd | Lifting Plan / Permit to Work | LP/PTW-00 |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 24/01/25 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  | To hoist down 1 unit forklift from lorry chassis, using forklift to unload case, uncrate, shift and position into factory premise |  |  |  |  |  |  |  |  |  |  |  |  |
| Location of lifting operation |  | 18 Woodlands Loop - Edmund Optics Singapore Pte Ltd |  |  |  |  |  |  |  |  |  |  |  |  |
| Date/time of lifting operation |  | 04/02/25 |  |  |  |  |  |  |  |  |  |  |  |  |
| Validity period of lifting operation |  | 1 day |  |  |  |  |  |  |  |  |  |  |  |  |
| - Details of Loads to be Hoist |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | 1 x forklift |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  | 2.8m x 1m x 2m |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 5, 000 kgs |  |  |  | Known weight |  |  |  | Estimated weight |  |  |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  |  |  | Determined by drawing |  |  |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Mobile crane |  |  |  |  |  |  |  |  | Lorry loader |  |  |
| LM/LE Registration No. |  |  | LM406824P |  |  |  |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 05/09/24 |  | Expiry date of certificate |  |  |  |  |  |  |  |  | 04/09/25 |
| Max. Safe Working Load |  |  | 16, 800 kg |  |  |  |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 22.40 m |  |  |  |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 6 m |  |  |  | SWL at this radius |  |  |  | 12, 200 kg |  |  |  |
| Type of lifting gears |  |  | Wire sling, shackle |  |  |  |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 60 kg |  |  | SWL of lifting gear |  |  |  |  |  | 4ton x 4pcs |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 26/11/25 |  |  |  |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  |  |  |  | Qualification / Experience |  |  |
| Site Supervisor |  | Ibrahim / Zahari / Koh Ban San |  |  |  |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Ibrahim / Zahari / Koh Ban San |  |  |  |  |  |  |  |  |  | Qualified lifting supervisor |  |  |
| Lifting Equipment Operator |  | Norhalim / Ngaimin / Ahmad |  |  |  |  |  |  |  |  |  | Qualified crane operator |  |  |
| Rigger/Signalman |  | Rizal / Hanifah / Aziz |  |  |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |
| Rigger/Signalman |  | Rahman / Malik / Kughanesswaran |  |  |  |  |  |  |  |  |  | Qualified rigger/signalman |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |  |  |  |
| 1.Deploy lorry loader back to back with container |  |  |  |  |  |  |  | Ibrahim / Zahari / Koh Ban San |  |  |  |  |  |  |
| 2.Lorry loader to hoist down forklift from lorry chassis to the ground |  |  |  |  |  |  |  | Ibrahim / Zahari / Koh Ban San |  |  |  |  |  |  |
| 3.Using crane to pull out case from container and load onto lorry container |  |  |  |  |  |  |  | Ibrahim / Zahari / Koh Ban San |  |  |  |  |  |  |
| 4.Using forklift to fork down cases to the ground |  |  |  |  |  |  |  | Ibrahim / Zahari / Koh Ban San |  |  |  |  |  |  |
| 5.Uncrate case and put aside |  |  |  |  |  |  |  | Ibrahim / Zahari / Koh Ban San |  |  |  |  |  |  |
| 6.Forklift to fork up and detach machine from base |  |  |  |  |  |  |  | Ibrahim / Zahari / Koh Ban San |  |  |  |  |  |  |
| 7.Transport and unload machine at loading bay |  |  |  |  |  |  |  | Ibrahim / Zahari / Koh Ban San |  |  |  |  |  |  |
| 8.Using rollers to shift and transport to 4th floor via cargo lift |  |  |  |  |  |  |  | Ibrahim / Zahari / Koh Ban San |  |  |  |  |  |  |
| 9.Position at the designated location |  |  |  |  |  |  |  | Ibrahim / Zahari / Koh Ban San |  |  |  |  |  |  |
| 10.Once job complete, proper housekeeping will be done |  |  |  |  |  |  |  | Ibrahim / Zahari / Koh Ban San |  |  |  |  |  |  |
| 11.All debris will be clear and disposed |  |  |  |  |  |  |  | Ibrahim / Zahari / Koh Ban San |  |  |  |  |  |  |
| 12.Job complete |  |  |  |  |  |  |  | Ibrahim / Zahari / Koh Ban San |  |  |  |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  |  | Signature: |  |  |  |  | Date: 04/02/25 |  |  |  |  |  |
| Prepared by: Zahari Designation: Lifting Supervisor |  |  |  | Signature: |  |  |  |  | Date: 04/02/25 |  |  |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  |  | Signature: |  |  |  |  | Date: 04/02/25 |  |  |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  |  | Signature: |  |  |  |  | Date: 04/02/25 |  |  |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |