| Eric Wong Machinery Transportation Pte Ltd | Lifting Plan / Permit to Work | LP/PTW-00 |  |
| --- | --- | --- | --- |
|  |  | Rev : 00 | Date: 28/08/25 |
|  |  | Page 1 of 2 |  |

| - General |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  | Shift out and hoist up 1 unit machine onto low bed |  |  |  |  |  |  |  |  |  |
| Location of lifting operation |  | 70 Joo Koon Circle – Nakano |  |  |  |  |  |  |  |  |  |
| Date/time of lifting operation |  | 30/08/25 - 09:45 am |  |  |  |  |  |  |  |  |  |
| Validity period of lifting operation |  | 1 day |  |  |  |  |  |  |  |  |  |
| - Details of Loads to be Hoist |  |  |  |  |  |  |  |  |  |  |  |
| Description of load: |  | 1 x 110ton Press machine |  |  |  |  |  |  |  |  |  |
| Overall dimension of load: |  |  |  |  |  |  |  |  |  |  |  |
| Weight of load: |  | 10, 000 kgs |  |  |  | Known weight |  |  | Estimated weight |  |  |
| Centre of gravity: |  | Obvious |  |  |  | Estimated |  |  | Determined by drawing |  |  |
| - Details of Lifting Equipment |  |  |  |  |  |  |  |  |  |  |  |
| Type of Lifting Equipment |  |  | Mobile crane |  |  |  |  |  | Lorry loader |  |  |
| LM/LE Registration No. |  |  | LM961229B |  |  |  |  |  |  |  |  |
| Date of last certification |  |  | 18/06/25 |  | Expiry date of certificate |  |  |  |  |  | 17/06/26 |
| Max. Safe Working Load |  |  | 20, 100 kg |  |  |  |  |  |  |  |  |
| Max. Boom/Jig length |  |  | 21.90 m |  |  |  |  |  |  |  |  |
| Intended load radius |  |  | 6 m |  |  |  | SWL at this radius |  | 14, 300 kg |  |  |
| Type of lifting gears |  |  | Wire sling |  |  |  |  |  |  |  |  |
| Combined weight of lifting gears |  |  | 100 kg |  |  | SWL of lifting gear |  |  | 4ton x 4pcs |  |  |
| Certification of lifting gears |  |  | Yes No |  |  |  |  |  |  |  |  |
| Expiry date of certificate |  |  | 15/10/25 |  |  |  |  |  |  |  |  |
| - Means of Communication |  |  |  |  |  |  |  |  |  |  |  |
| Can the operator see the loading and unloading for the load from his position? |  |  |  |  |  | Yes No |  |  |  |  |  |
| What at the means of communication between the lifting crew? |  |  |  |  |  | Standard hand signals Radio Others_____________________________ |  |  |  |  |  |
| - Personnel Involved in Lifting Operation |  |  |  |  |  |  |  |  |  |  |  |
| Position |  | Name |  |  |  |  |  |  | Qualification / Experience |  |  |
| Site Supervisor |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |  |  |  |  |  |
| Lifting Supervisor |  | Wong Yen Siong / Koh Ban San / Zahari / Ibrahim |  |  |  |  |  |  | Qualified lifting supervisor |  |  |
| Lifting Equipment Operator |  | Lim Poh Soon / Lim Poh Thiam |  |  |  |  |  |  | Qualified crane operator |  |  |
| Rigger/Signalman |  | Aziz / Sing Kwok Liang / Hanifah / Vignesh |  |  |  |  |  |  | Qualified rigger/signalman |  |  |
| Rigger/Signalman |  | Malik / Ahmad / Sarawanan / Rizal / Ibrahim |  |  |  |  |  |  | Qualified rigger/signalman |  |  |
| - Physical and Environmental Considerations |  |  |  |  |  |  |  |  |  |  |  |
| Ground condition | Is the ground made safe (eg: placing steel plate) |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are the outriggers evenly extended? |  |  |  |  |  |  |  |  | Yes No |  |
| Obstacles | Are there any overhead obstacles? |  |  |  |  |  |  |  |  | Yes No |  |
|  | Are there structure, equipment, stacked materials, etc that obstruct lifting operation from being carried out safely? |  |  |  |  |  |  |  |  | Yes No |  |
| Lighting | Is the lighting condition adequate? |  |  |  |  |  |  |  |  | Yes No |  |
| Demarcation | Has the zone of operation been barricade (with warning signs and barriers) to prevent unauthorised access? |  |  |  |  |  |  |  |  | Yes No |  |
| Other Precautions: |  |  |  |  |  |  |  |  |  |  |  |
| - Tasks |  |  |  |  |  |  |  |  |  |  |  |
| Sequence of lifting Operations: |  |  |  |  |  |  |  | Person in Charge for each step |  |  |  |
| 1.Jack up machine to 4” high |  |  |  |  |  |  |  | Zahari / Koh Ban San / Wong Yen Siong |  |  |  |
| 2.Insert rollers under machine bed |  |  |  |  |  |  |  | Zahari / Koh Ban San / Wong Yen Siong |  |  |  |
| 3.Shift out machine to loading bay |  |  |  |  |  |  |  | Zahari / Koh Ban San / Wong Yen Siong |  |  |  |
| 4.Riggers to insert required lifting gears to crane hook |  |  |  |  |  |  |  | Zahari / Koh Ban San / Wong Yen Siong |  |  |  |
| 5.Secured sling to machine rigging point |  |  |  |  |  |  |  | Zahari / Koh Ban San / Wong Yen Siong |  |  |  |
| 6.1 x lorry crane to hoist up machine |  |  |  |  |  |  |  | Zahari / Koh Ban San / Wong Yen Siong |  |  |  |
| 7.1 x lorry crane to assist to lay down machine to horizontal position |  |  |  |  |  |  |  | Zahari / Koh Ban San / Wong Yen Siong |  |  |  |
| 8.Hoist up machine and load onto low bed |  |  |  |  |  |  |  | Zahari / Koh Ban San / Wong Yen Siong |  |  |  |
| 9.Secured machine with chain lock |  |  |  |  |  |  |  | Zahari / Koh Ban San / Wong Yen Siong |  |  |  |
| 10.Transport out machine and deliver to Eric Wong warehouse |  |  |  |  |  |  |  | Zahari / Koh Ban San / Wong Yen Siong |  |  |  |
| 11.Once job complete, proper housekeeping will be done |  |  |  |  |  |  |  | Zahari / Koh Ban San / Wong Yen Siong |  |  |  |
| 12.All debris will be clear and disposed |  |  |  |  |  |  |  | Zahari / Koh Ban San / Wong Yen Siong |  |  |  |
| 13.Job complete |  |  |  |  |  |  |  | Zahari / Koh Ban San / Wong Yen Siong |  |  |  |
| - Approval of Lifting Plan |  |  |  |  |  |  |  |  |  |  |  |
| Applied by: Zailani Designation: Supervisor |  |  |  | Signature: |  |  |  | Date: 28/08/25 |  |  |  |
| Prepared by: Wong Yen Siong Designation: Lifting Supervisor |  |  |  | Signature: |  |  |  | Date: 28/08/25 |  |  |  |
| Assessed by: Kevin Wong Designation: Project Manager |  |  |  | Signature: |  |  |  | Date: 28/08/25 |  |  |  |
| Approved by: Eric Wong Designation: Managing Director |  |  |  | Signature: |  |  |  | Date: 28/08/25 |  |  |  |
| This lifting plan shall be prepared by the lifting supervisor. The Department Head responsible shall approve the lifting plan / permit to work |  |  |  |  |  |  |  |  |  |  |  |