# METHOD OF STATEMENT

Date: 20th Aug 2024

Description of work

To shift out machine and accessories from production area to loading bay, hoist up onto wooden base for packing, after packing, load onto estimate 1 x 40ft OT, 2 x 40ft HQ and 2 x 40ft FR container

Machine Spec

Refer to attached list

Toshiba TUE-150

Toshiba BTD-110-R16

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

Estimate:

26-27/08/24 (move out for packing)

28/08/24 (load onto 2 x 40ft HQ & 1 x 40ft OT container)

29/08/24 (load onto 2 x 40ft FR)

Time of Operation

09:45 am

Location of Operation

#### 15 Pioneer Sector 3

Fong Lee Metal Industries Pte Ltd

Equipment Use

1 x 50ton mobile crane

633 lorry loader

1 x forklift

Hydraulic/hand jack

Rollers/pallet truck

Woodblock

Wire/webbing sling

Shackle

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and disposed

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crew certificate)

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deploy mobile/lorry crane at designated hoisting location

- Set up crane with outriggers fully extended and resting on steel plate/timber mats for base plate

- Jack up machine to 4” high

- Insert rollers under machine

- Shift out machine from production to loading area

- Riggers to attached sling to crane hook

- Secure sling to rigging point of machine

- Hoist up machine 1ft above ground to check on stability

- When well balanced hoist up machine

- Load up machine onto wooden for packing

- Pack to form a case

- After packing hoist and load up case onto customer arrange container

- Secured case with lashing belt and choking wood

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175