# METHOD OF STATEMENT

Date: 03rd July 2024

Description of work

To shift out 1 unit machine from production area to loading bay, assist customer engineer to dismantle machine head, after dismantle load up onto 1 x 40ft FR, 1 x 40ft OT. 1 x 20ft GP and   1 x 40ft HQ container

Machine Spec

1 unit Gemini GHT11-G4-2000X6000

Main machine: 1050 x 220 x 100 cm / Wt: 43, 000 kg

Chip Conveyor: 1100 x 80 x 270 cm / Wt: 4, 500 kg

Chuck: 160 x 190 x 160 cm / 5, 000 kg

Head: 220 x 200 x 200 cm / 20, 000 kg

Motor: 175 x 135 x 170 cm / Wt: 3, 000 kg

Electric Panel: 380 x 80 x 250 cm / Wt: 3, 000 kg

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

Estimate 3 day job:

04/07/24 (jack up machine to cut off all stud and standby for Sat moving)

06/07/24 (shift out accessories and load onto container using forklift)

08/07/24 (shift out machine to loading area, hoist and load onto container)

Time of Operation

09:45 am

Location of Operation

#### 149 Gul Circle

#### FMC Technologies Singapore Pte Ltd

Equipment Use

1 x 200ton mobile crane

Lorry loader

1 x 7ton forklift

Hydraulic jack

Woodblock

Rollers/electric rollers

Pallet truck

Wire/webbing sling

Shackle

Hand grinder (to cut off low plug)

Obstacles

No obstacle on operation area and route to machine position

Barricade off operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose after job completion

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crew certificate)

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deployment of mobile crane at designated hoisting area

- Jack up machine to 4” high and let it sit on solid woodblock

- To cut off all stud

- Insert rollers under machine bed

- Shift out machine from workshop to loading area

- To assist customer engineer to dismantle machine head

- Riggers to attached required sling lifting to crane hook

- Secure sling to rigging point of load to be lifted

- Once rigging work is done, signalman to give signal to crane operator to hoist up machine

- Load up machine onto container

- Release all sling from rigging point of machine

- Secured machine with lashing belt and chocking wood

- Using 7ton forklift to fork and load up accessories onto container

- Secured machine with lashing belt and chocking wood

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and disposed

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175