# METHOD OF STATEMENT

Date: 10th Sep 2024

Description of work

To shift out 1 unit machine and accessories from production area to loading bay, hoist up and load onto wooden base for your packers to pack

Machine Spec

1 unit Mazak E650H

Wt: 32, 200 kg

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

Estimate 3 day job

18/09/24 (jack up machine to cut off all stud)

19/09/24 (shift out accessories to loading area for your packer to pack)

20/09/24 (shift out machine to loading area, hoist up onto wooden base for your packer to pack)

Time of Operation

09:45 am

Location of Operation

#### 149 Gul Circle

#### FMC Technologies Singapore Pte Ltd

Equipment Use

1 x 100ton mobile crane

Lorry loader

1 x forklift

Hydraulic jack

Woodblock

Rollers/electric rollers

Pallet truck

Wire/webbing sling

Shackle

Hand grinder (to cut off low plug)

Obstacles

No obstacle on operation area and route to machine position

Barricade off operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose after job completion

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crew certificate)

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deployment of mobile crane at designated hoisting area

- Jack up machine to 4” high and let it sit on solid woodblock

- To cut off all stud

- Insert rollers under machine bed

- Shift out machine from workshop to loading area

- Riggers to attached required sling lifting to crane hook

- Secure sling to rigging point of load to be lifted

- Once rigging work is done, signalman to give signal to crane operator to hoist up machine

- Load up machine onto wooden base for your packer to pack

- Release all sling from rigging point of machine

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and disposed

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175