# METHOD OF STATEMENT

Date: 17th Apr 2025

Description of work

To shift out 2 units machine and accessories from production area to loading bay, hoist up onto customer arrange container

Machine Spec

Mazak FH6800

Dim: 550 x 280 x 275 cm each

Wt: 19, 700 kg each

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

Estimate 3 days job:

28/04/25 – shift out accessories and load up onto container

29-30/04/25 – shift out machine and load up onto container

Time of Operation

10:00 am

Location of Operation

#### 16 Seletar Aerospace Crescent

JEP Precision Engineering Pte Ltd

Equipment Use

633 lorry loader

Low loader

1 x forklift

Hydraulic/hand jack

Rollers/pallet truck

Wire/webbing sling

Metal plate/canvas (to lay out for floor protection)

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and disposed

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and lorry crane operator will be involved in this operation (attached all lifting crew certificate)

Safety Aspect

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deployment of lorry crane at designated hoisting location

- Set up crane with outrigger fully extended and resting on steel plate/timber mats as base plate

- To jack up machine to 4” high

- Insert rollers under machine bed

- Shift out machine from production to loading area

- Riggers to attached required sling onto crane hook

- Secure sling to rigging point of machine

- Hoist up machine 1ft above ground to check on balancing

- When well balanced, hoist and load up machine onto low loader

- Released all sling from rigging point of machine

- Transport low loader to outside factory

- Hoist machine and transfer onto FR container

- Secured machine with chocking wood and lashing belt

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175