# METHOD OF STATEMENT

Date: 22nd Sep 2020

Description of work

1) To shift out 1 unit machine from production area to loading bay and put aside, next day hoist up onto low-loader

2) To unload 1 unit machine from low-loader, shift and positon into production area

Machine Spec

Move Out

1 unit Komatsu Single Crank Press

Move In

1 unit Aida 200 Double Crank Press

Dim: 4m x 2.8m x 2.9m

Wt: 25, 000 kg

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

28/09/20   -   Shift out from production and put aside

29/09/20   -   Unload machine from low-loader, upright, shift and position into production

Time of Operation

09:45 am

Location of Operation

#### 70 Joo Koon Circle

Nakano Metal Press (S) Pte Ltd

Equipment Use

1 x 70ton mobile crane

1-2 x 633 lorry loader

1 x low-loader

1 x forklift

Rollers/pallet truck

8-10 ton wire sling

Shackle

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and disposed

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman, mobile and lorry crane operator will be involved in this operation (attached all lifting crew certificate)

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

Move out

- Jack up machine

- Insert rollers under machine bed

- Shift out machine from production to loading area

- Put machine aside, next day hoist up onto low-loader

Move in

- Deploy mobile crane and lorry loader at designated hoisting area

- Reverse low-loader to near crane

- Mobile crane to hoist down machine from low-loader

- Unload machine to the ground

- Using mobile crane and lorry loader to upright machine

- Insert rollers under machine bed

- Shift and transport machine into production area

- Position machine at the designated location

- Jack up machine and insert levelling pad under machine bed

- To hoist up Komatsu single crank press and load onto low-loader

- Secured machine with strapping belt prior to moving out of premise

- Transport and deliver to Eric Wong warehouse

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175