# METHOD OF STATEMENT

Date: 16th Oct 2025

Description of Work

To unload 1 unit machine and accessories from 1 x 20ft FR and 1 x 20GP container, shift and position into production area at ground floor

Machine Spec

1 unit Yamada Dobby Press / MXM-80L-0181

Dim: 376 x 208 x 358 cm

Wt: 20, 500 kg

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

Est:

24/10/25 – 27/10/25

Time of Operation

09:30 am

Location of Operation

#### 110 International Rd, Jurong Town

Molek Singapore Pte Ltd

Equipment Use

110ton lorry loader

633 lorry loader

1 x short tail low bed

Rollers/pallet truck

Wire/webbing sling

Shackle

Hydraulic jack

Canvas/metal sheet (to lay out for floor protection)

Metal plate

Obstacles

No obstacles on crane parking area and route to machine position

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carried out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and lorry loader operator will be involved in this operation (attached all lifting crew certificate)

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deploy lorry crane at designated unloading area for the lifting work

- Set up crane with outrigger fully extended and resting on timber mats as base plate

- Rigger to insert sling to lorry crane hook and secured to rigging point of machine

- Hoist up machine from FR container and load up onto short low bed

- Transfer low bed to back of factory door entrance

- Lorry crane to hoist down machine and lower down to near ground level

- Insert rollers under machine bed

- Shift and transport machine into factory premise at ground floor

- Position machine at the designated location

- Unload machine form rollers and insert levelling pad under machine base

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175