# METHOD OF STATEMENT

Date: 18th Dec 2025

Description of Work

To unload 4 steel cases of 1 unit machine from low-bed, 1 x 20ft FR and 1 x 40ft HQ container, uncrate, shift and position into production area at ground floor

Machine Spec

DMU 125P Machine

Case 1: 6500 x 3500 x 3950 mm

N/G wt: 21, 000 kg / 25, 000 kg

Case 2: 5000 x 3000 x 3700 mm

N/G wt: 8, 500 kg / 9, 800 kg

Case 3: 6100 x 2300 x 240 mm

N/G wt: 1, 350 kg / 1, 950 kg

Case 4: 3500 x 2300 x 2400 mm

N/G wt: 900 kg / 1, 300 kg

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

Estimate:

30/12/25 – to lay out metal plate and unload accessories

08/01/26 – to unload machine

Time of Operation

10:00 am

Location of Operation

#### 16 Seletar Aerospace Crescent

JEP Precision Engineering Pte Ltd

Equipment Use

1 x 100ton mobile crane

1-2 x 633 lorry loader

1 x forklift

Rollers/pallet truck

Wire/webbing sling

Shackle

Manual/hydraulic jack

Metal plate/canvas (to lay out for floor protection)

Obstacles

No obstacles on crane parking area and route to machine position

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crew certificate)

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deploy mobile crane at designated hoisting location

- Set up crane with outriggers fully extended and resting on steel plate/timber mats as base plate

- Reverse low-bed to near crane

- Insert sling below machine case

- Hoist down case from low-bed to the ground

- Uncrate case and put aside

- Riggers to insert sling to crane hook

- Secured sling to rigging point of machine

- Hoist up and detach machine from base

- Swing machine away from base

- Lower down machine to near ground level

- Insert rollers under machine bed

- Shift and transport machine into factory premise at ground floor

- Position machine at the designated location

- Unload machine form rollers and insert levelling pad under machine base

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175