# METHOD OF STATEMENT

Date: 26th June 2024

Description of work

To hoist down 1 unit machine and accessories from low loaders/lorry chassis, shift and position into factory premise at ground floor

Machine Spec

1 unit Nigata machine

Dim: 5.73 x 3.3 x 3.55

Wt: 20, 500 kg

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

01/07/24 – to unload and move in machine accessories

02/07/24 – to unload and move in main machine

Time of Operation

Est: 11:30 am

Location of Operation

#### 16E Tuas Ave 1 #01-61

Hunting Energy Services Pte Ltd

Equipment Use

1 x 50 ton mobile crane

Lorry loader

1 x low loader

1 x forklift

Hydraulic rollers

Pallet truck

Hydraulic jack

Wire/webbing sling

Shackle

Metal sheet/canvas (to lay out for floor protection)

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carried out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crews certificate)

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)                                                                                                                                                Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deploy mobile crane at designated unloading area

- Setting up crane on site with outrigger fully extended and resting on metal plate/timber mats as base plate

- To reverse low loader to near crane

- Riggers to attached sling to crane hook

- Secure sling to rigging point of machine

- Hoist up machine from low loader

- Move out low loader away

- Lower down machine slowly to near ground level

- Insert hydraulic rollers to machine base

- Secured rollers with bolts and nuts

- Transport machine into factory premise

- Position machine at the designated location

- Jack up machine, pull out rollers and insert levelling pad under machine bed

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175