# METHOD OF STATEMENT

Date: 13th Sep 2021

Description of work

To unload 2 cases of 1 unit machine from customer arrange container, uncrate, shift and transport to 4th floor via cargo lift

Machine Spec

Vacuum Coater LP-1300EBA

Case 1: 360 x 230 x 256 cm / Wt: 3, 390 kg

Case 2: 380 x 230 x 255 cm / Wt: 2, 260 kg

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

15/09/2021

Time of Operation

09:45 am

Location of Operation

#### 18 Woodlands Loop

Edmund Optics (S) Pte Ltd

Equipment Use

1 x 633 lorry loader

Rollers/pallet truck

Wire/webbing sling

Plywood/metal plate (for lay out for epoxy floor protection)

Obstacles

No obstacle on crane parking area and route to machine positioning

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carried out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and lorry loader operator will be involved in this operation (attached all lifting crews certificate)

Safety Aspect

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)                                                                                                                                                Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deploy lorry loader at designated unloading area (back to back with container)

- Pull out machine case from container onto lorry chassis

- Hoist down case to the ground

- Uncrate case

- Hoist up and detach machine from base

- Load machine onto lorry chassis

- Secure machine with strapping belt

- Reverse lorry to loading bay

- Insert pallet truck/rollers under machine bed

- Shift out machine from lorry chassis

- Transport machine to 4th floor via cargo lift

- Position machine at the designated location

- Unload machine from pallet truck/rollers and insert levelling pad under machine bed

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175