# METHOD OF STATEMENT

Date: 17th Sep 2024

Description of work

To hoist down 1 unit machine with parts from low loader, assemble outside of tenant premise, shift and position into factory premise at ground floor

Machine Spec

1 unit Wele LB-321YZ2M machine

Dim: 875 x 404 x 315 cm / Wt: 25, 500 kg

Dim: 488 x 336 x 360 cm / Wt: 14, 000 kg

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

Estimate:

19/09/24  -  23/09/24

Time of Operation

10:00 am

Location of Operation

#### Blk 20 A.M.K Industrial Pk 2A #01-02

Fujitson

Equipment Use

1 x 100 ton mobile crane

Lorry loader

1 x low loader

Hydraulic rollers

Hydraulic jack

Wire/webbing

Shackle

1 x forklift

Metal sheet/canvas (to lay out for floor protection)

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carried out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

P.P.E Required

Safety shoe

Safety helmet

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)                                                                                                                                                Lifting machine and lifting gear with M.O.M certificate

Lifting crew shall be composed to the following but not limited by other trained personnel in respect to number of crew needed for the operation:

a. Lifting Supervisor

b. Mobile Crane Operator

c. Lorry Loader Operator

d. Signalman

e. Riggerman

f. Skill Mover

# JOB SCOPE

- Deploy mobile crane at designated unloading area

- Setting up crane on site with outriggers fully extended and resting on steel plate/timber mats as base plate

- Barricade off work area with safety cones, red/white tape and lifting in operation signage

- To reverse low loader to near mobile crane

- Riggers to attached sling to crane hook

- Secure sling to rigging point of machine

- Hoist up machine from low loader

- Move out low loader away

- Lower down machine slowly to near ground level

- Insert hydraulic rollers under machine bed

- Secured rollers with bolts and nuts

- Transport machine into factory premise

- Position machine at the designated location

- Jack up machine, pull out rollers and insert levelling pad under machine bed

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175