# METHOD OF STATEMENT

Date: 02nd Jan 2025

Description of work

To hoist up 1 unit equipment to 3rd floor through door opening by using platform and lorry crane

Spec

1 unit Vertical Storage Carousal

Dim: 2390 x 1640 x 2510 mm

Wt: 1, 700 kg

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

18/01/25 (Sat)

Time of Operation

10:00 am

Location of Operation

#### 28 Ayer Rajah Crescent

Fitson Singapore Pte Ltd

Equipment Use

2 x 633 lorry loader

1 x platform

1 set wire/webbing sling

Shackle

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

P.P.E Required

Safety Helmet

Safety Shoe

Safety Harness

Self Retracting Lifeline

Safety Aspect

1) Assignment of traffic controller to control and guide movement of vehicle and personnel within the vicinity

2) Barricade off work area with safety cones, red/white tape and lifting in operation signage

3) All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            4) Lifting machine and lifting gear with M.O.M certificate

5) Lifting crew shall be composed to the following but not limited by other trained personnel in respect to the number of crew needed for the operation:

a. Lifting Supervisor

b. Lorry Loader Operator

c. Riggerman

d. Signalman

e. Skill Mover

# JOB SCOPE

- Deployment of 2 x lorry crane at designated hoisting area for the lift

- Setting up of crane with outriggers fully extended and resting on steel plate/timber mats as base plate

- Hoist up platform to 3rd floor door opening

- Stabilize platform effectively and ensure platform 3ft metal protruding is fully lean and rested on the opening slab

- Tied back platform to a competent point and secured using 1 x lorry crane

- Use strong belt to secure front left and right of platform onto building railing/pillar to prevent platform swing outward

- 1 x lorry crane to hoist up equipment to 3rd floor

- Lower down equipment onto platform

- Insert pallet truck under equipment base

- Shift out from platform and position into customer premise

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175