# METHOD OF STATEMENT

Date: 10th Dec 2020

Description of work

To unload 9 cases of 1 unit machine from customer arranged container/cometto, uncrate, shift and position into customer premise at ground floor

Machine Spec

1 unit Mega II-260 x 8000 machine

Case 1: 3000 x 2200 x 2720 mm     N/G Wt: 22, 000 kgs / 22, 718 kgs

Case 2: 3700 x 2350 x 2800 mm     N/G Wt: 20, 000 kgs / 20, 974 kgs

Case 3: 13100 x 4200 x 1850 mm   N/G Wt: 72, 230 kgs / 76, 301 kgs

Case 4: 10300 x 2200 x 2650 mm   N/G Wt: 5, 900 kgs / 8, 302 kgs

Case 5: 2800 x 2000 x 2500 mm     N/G Wt: 6, 000 kgs / 6 560 kgs

Case 6: 3000 x 2200 x 1600 mm     N/G Wt: 8, 000 kgs / 8, 422 kgs

Case 7: 2400 x 1500 x 1000 mm     N/G Wt: 3, 000 kgs / 3, 144 kgs

Case 8: 2800 x 2300 x 1500 mm     N/G Wt: 3, 000 kgs / 3, 386 kgs

Case 9: 2800 x 2300 x 1500 mm     N/G Wt: 15, 000 kgs / 15, 144 kgs

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

Est: 12-19/12/2020

Time of Operation

10:00 am

Location of Operation

#### 3 Joo Koon Circle

AME International Pte Ltd

Equipment Use

2 x 100 ton mobile crane

1 x cometto

Lorry loader

1 x forklift

Heavy duty rollers

Wire/webbing sling

Metal sheet/canvas (for floor protection)

Shackle

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carried out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crews certificate)

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet, safety harness)                                                                                                                                                Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deploy 2 x 100 ton mobile crane at designated unloading bay

- Setting up of crane on site with outriggers fully extended and resting on steel plate as base plate

- Transport cometto to near crane

- Insert wire sling under machine case

- Using 2 x mobile crane to hoist up case from cometto

- Move out cometto

- Lower down case to the ground

- Uncrate case

- Attached required lifting gears onto crane hook and secured to rigging point of machine to be lifted

- Hoist up and detach machine from base

- Shift base away

- Lower down machine slowly to near ground level

- Insert heavy duty rollers to machine base and secured with bolts and nuts

- Transport machine into production area

- Position machine at the designated location

- Jack up machine, pull out rollers and insert levelling pad under machine bed

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175