# METHOD OF STATEMENT

Date: 20th June 2025

Description of work

To shift out 1 unit press machine from production room to loading area, hoist and lay down machine, load up onto FR container

Machine Spec

1 unit Seyi SN2-200 Press

Wt: 27, 000 kg

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

24/06/25

Time of Operation

09:45 am

Location of Operation

#### 38 Benoi Place

Civic International Pte Ltd

Equipment Use

1 x 50ton mobile crane

1 x 633 lorry crane

1 x forklift

Heavy duty rollers

Wire sling

Shackle

Obstacles

No obstacle on crane parking area

Barricade off operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and disposed

P.P.E Required

Safety helmet

Safety shoe

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed

Lifting machine and lifting gear with M.O.M certificate

Lifting crew shall be composed to the following but not limited by other trained personnel in respect to number of crew needed for the operation:

a. Lifting Supervisor

b. Mobile Crane Operator

c. Lorry Crane Operator

d. Signalman

e. Riggerman

f. Skill Mover

# JOB SCOPE

- Jack up machine to 4” high

- Insert rollers to machine base

- Shift out machine from production to loading bay

- Rigger to attached required lifting gears to crane hook

- Secured sling to rigging point of machine

- Hoist up machine 1ft above ground

- Use 55ton lorry loader to assist laying down machine to horizontal position

- Hoist up machine and load onto container

- Secured machine with chocking wood and lashing belt

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175