# METHOD OF STATEMENT

Date: 19th Aug 2024

Description of Work

To unload 3 cases of 1 unit machine and accessories from 1 x 40ft FR container, uncrate, shift and position into production area at ground floor

Machine Spec

1 unit FJV-35/60

Case 1: 545 x 343 x 339 cm / Wt: 19, 000 kg

Case 2: 335 x 147 x 168 cm / Wt: 630 kg

Case 3: 121 x 94 x 57 cm / Wt: 220 kg

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

21/08/24

Time of Operation

10:00 am

Location of Operation

#### 6 Loyang Walk

Fidel

Equipment Use

1 x 50ton mobile crane

633 lorry loader

1 x forklift

Electric roller/rollers/pallet truck

Wire sling

Webbing sling

Shackle

Hydraulic jack

Metal plate/canvas (to lay out for epoxy floor protection)

Obstacles

No obstacles on crane parking area and route to machine position

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and lorry crane operator will be involved in this operation (attached all lifting crews certificate)

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deployment of mobile crane at designated unloading area

- Setting up crane with outrigger fully extended and resting on metal plate/timber mats as base plate

- Insert sling under machine case

- Hoist down case from FR container to the ground

- Uncrate case and put aside

- Riggers to insert sling to crane hook

- Secured sling to rigging point of machine

- Signalman to give signal to crane operator to hoist up and detach machine from base

- Swing machine away from base

- Lower down machine to near ground level

- Insert rollers under machine bed

- Shift and transport machine into factory premise at ground floor

- Position machine at the designated location

- Unload machine form rollers and insert leveling pad under machine bed

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175