# METHOD OF STATEMENT

Date: 13th July 2022

Description of work

To unload 2 packages of 1 unit machine from 1 x 20ft FR container, uncrate, shift and position into factory premise at ground floor

Machine Spec

1 unit Press Brake machine

Case 1: 393 x 231 x 307 cm / N/Wt: 9, 060 kg

Case 2: 137 x 137 x 111 cm / N/Wt: 480 kg

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

Estimate:

15-18/07/22

Time of Operation

09:45 am

Location of Operation

#### 18 Joo Koon Circle

Yamazaki Mazak Singapore Pte Ltd

Equipment Use

1 x 633 lorry loader

Wire sling

Shackle

Rollers

Pallet truck

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carried out on heavy rain, thunderstorms and lightning weather

All debris will be clear and disposed

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and lorry crane operator will be involved in this operation (attached all lifting crews certificate)

Safety Aspect

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)                                                                                                                                                Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deploy lorry loader at designated location for the hoisting

- Hoist down case from FR container to the ground

- Uncrate case and put aside

- Hoist up and detach machine from base

- Swing machine away from base

- Lower down machine to near ground level

- Insert rollers under machine bed

- Shift and transport machine into factory premise

- Position at the designated location

- Unload from rollers and insert levelling pad under machine bed

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and disposed

- Job complete

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175