# METHOD OF STATEMENT

Date: 28th Oct 2025

Description of work

To unload 11 cases of 1 unit machine from 1 x heavy duty low-bed, 1 x 50ft trailer and 2 x 40ft trailer, uncrate, shift and position into customer premise at ground floor

Machine Spec

11 cases of 1 unit Niles Simmons M/N30MC

Refer to attached

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

30/10/25 – unload accessories using lorry loader

31/10/25 – unload machine using mobile crane

Time of Operation

10:00 am

Location of Operation

#### No 51 Seletar Aerospace View

Pratt & Whitney NGPF Manufacturing Company Pte Ltd

Equipment Use

2 x 100ton mobile crane

Lorry loader

Heavy duty roller

Pallet truck

Wire sling

Webbing sling

Shackle

Hydraulic jack

Metal sheet/canvas (to lay out for floor protection)

2 x scissor lift

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carried out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crew certificate)

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet, safety harness)                                                                                                                                                Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deployment of 2 x mobile crane at designated unloading area

- Set up crane with outrigger fully extended and resting on steel plate as base plate

- Insert wire sling under machine case

- Using 2 x mobile crane to slowly hoist up machine case

- Unload case from low-bed to the ground

- Uncrate case with the use of boom/scissor lifter

- After uncrate, hoist up machine and detach from base

- Lower down machine slowly to near ground level

- Insert heavy duty rollers to machine base and secured with bolts and nuts

- Transport machine into production area

- Position machine at the designated location

- Jack up machine, pull out rollers and insert levelling pad under machine bed

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175