# METHOD OF STATEMENT

Date: 09th Oct 2018

Description of work

To hoist up 1 unit machine to 3rd floor by using platform and mobile/lorry crane

Machine Spec

1 unit Horizontal Turning Centre   /   Model: NL502C

Dim: 4.5m x 2.15m x 2.35m

Wt: 4, 300 kgs

Risk Assessment

A copy of Risk Assessment will be attach

Date / Time of Operation

13/10/2018   -   Afternoon schedule

Location of Operation

#### 37 Kim Chuan Drive

Lokit Polymer Pte Ltd

Equipment Use

1 x 50 ton mobile crane

1 x 45/50 ton lorry crane

1 x platform

Wire sling

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and lorry/mobile crane operator will be involved in this operation

Safety Aspect

Assignment of traffic controller to control and guide movement of vehicle and personnel within the vicinity

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoe, safety helmet, safety harness)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Mobile/lorry crane to park at designated hoisting area for the lift

- Hoist up platform to 3rd floor opening

- Stabilize platform effectively and ensure it is fully rested on the opening slab

- Tied back platform to a competent point and secured using 45/50 ton lorry crane

- Use strong belt to secure front left and right of platform onto building railing/pillar to prevent platform swing outward

- 50 ton mobile crane to hoist up machine to 3rd floor

- Lower down machine onto platform

- Insert rollers/pallet truck to machine base

- Shift out machine from platform and position into customer premise

- Once job complete, team leader will instruct the team to perform proper housekeeping, all debris will be clear and dispose

- Job complete

Remark:

MOS subject to change by supervisor/lifting supervisor on site

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175