# METHOD OF STATEMENT

Date: 19th Dec 2023

Description of work

To hoist up 1 unit machine to 4th floor through shutter door opening by using platform and mobile crane

Machine Spec

1 unit DYHC 1000 ARC Coating machine

Dim: 412 x 227 x 310 cm

Wt: 7, 000 kg

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

27/12/23

Time of Operation

9:45 am

Location of Operation

#### 3 Toh Guan Rd East 4th Level

#### Knight Auto Precision Engineering Pte Ltd

Equipment Use

1 x 70 ton mobile crane

2 x lorry crane

1 x platform

1 x 10ton forklift

1 set wire sling

Shackle

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crew certificate)

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet, safety harness)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deploy mobile crane at designated hoisting area for the lift

- Using of 10ton forklift to fork and detach machine from base

- Load up machine onto platform

- Secured machine onto platform with strapping belt

- Mobile crane to hoist up platform together with machine to 4th floor swing gate opening

- Stabilize platform effectively and ensure platform 3ft metal protruding is fully lean and rested on the shutter door opening slab

- Use strong belt to secure front left and right of platform onto building railing/pillar to prevent platform swing outward

- Insert rollers under machine bed

- Use of manual pulley to slowly release and control moving speed of machine

- Shift out machine from platform

- Position machine to the designated location

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris, if any will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175