# METHOD OF STATEMENT

Date: 14th Feb 2020

Description of work

To hoist up 1 unit machine to 6th floor through swing gate opening by using platform and mobile crane

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

22/02/2020 (Saturday)

Time of Operation

09:30 am

Location of Operation

#### Blk 3014A Ubi Rd 1 #06-13

#### OMGA Pte Ltd

Equipment Use

1 x 50 ton mobile crane

2 x lorry crane

1 x platform

1 set wire/webbing sling

Shackle

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crew certificate)

Safety Aspect

Assignment of traffic controller to control movement of vehicle and personnel within the vicinity

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet, safety harness)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deployment of mobile/lorry crane at designated hoisting area

- Load machine onto platform

- Secured machine onto platform with strapping belt

- 1 x 50ton mobile crane to hoist up platform together with machine to 6th floor swing gate opening

- Stabilize platform effectively and ensure platform 3ft metal plate protruding is fully lean and rested on the building opening slab

- Use strong belt to secure front left and right of platform onto building railing/pillar to prevent platform swing outward

- Insert rollers/pallet truck under machine base

- Shift out machine from platform

- Position machine at the designated location

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175