# METHOD OF STATEMENT

Date: 13th Jan 2020

Description of Work

To assist engineer to dismantle 1 unit machine to 4 parts using gantry crane, after dismantle, shift out to loading bay, hoist up and load onto Malaysia low loader/lorry

Machine Spec

1 unit Aida PMX Power Press

Dim: 320 x 280 x 380 cm

Wt: 45, 000 kgs

1 x Straightener

Dim: 200 x 110 x 170 cm

1 x NC Feeder

Dim: 410 x 300 x 230 cm

1 x Robot

Dim: 180 x 160 x 200 cm

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

17/01/2020   -   Jack up machine and put aside

18/01/2020   -   To shift out machine and parts to loading bay, hoist up and load onto lorry/low loader and deliver to another location

Time of operation

09:45 am

Location of Operation

No 20 Benoi Sector

Shimano (S) Pte Ltd

Equipment Use

1 set hydraulic gantry crane

1 x 160ton mobile crane

1 x 633 lorry loader

1 x 4.5 ton forklift

1 set heavy duty rollers

1 set 15ton wire sling

4 pcs 25ton shackle

4-8 pcs 17ton shackle

Obstacles

To clear all obstacles around working area

Barricade work area to prevent persons who are not involved enter unintentionally

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman, mobile/lorry crane operator and forklift operator will be involved in this operation

Safety Aspect

Barricade work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Setting up of gantry crane structure at location

- Secure wire sling to machine lifting point onto gantry crane

- Lift up machine part to the required height

- Shift out gantry crane

- Lower down machine part to near ground level

- Insert rollers below machinery bed

- Use forklift to pull machine out from production to loading bay

- 160ton mobile crane to hoist up machine onto low loader

- Lower down machine slowly and let it sit onto wood block

- Secured machine firmly with belts

- Guide low loader driver out of customer premise

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and disposed

- Job complete

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175