# METHOD OF STATEMENT

Date: 08th Mar 2022

Description of work

To shift out following machine and parts from production to loading area, hoist up onto lorry chassis and deliver to new location

Machine Spec

Refer to attached list

Risk Assessment

A copy of Risk Assessment will be attach

Schedule of Operation

Estimate: 01/04/22 - 14/04/22

Time of Operation

09:45 am

Location of Operation

#### Move out:

#### 33 Tuas Ave 2, Plant 9 – ST Kinetic Integrated Engineering Pte Ltd

Move in:

16 Tuas Ave 7 – ST Kinetics Singapore

Equipment Use

633 lorry loader

1 x forklift

Rollers / pallet truck

Hand jack / crowbar

Wire / webbing sling

Shackle

Obstacles

No obstacle on crane parking area and route of moving operation

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and disposed

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and lorry crane operator will be involve in this operation

Safety Aspect

Assignment of traffic controller to control movement of vehicle and personnel within the vicinity

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Jack up machine to 3” high

- Insert rollers/pallet truck under machine bed

- Shift out machine from production to hoisting bay

- Attached required lifting gears to crane hook and secured to hoisting rigging point of load to be lifted

- Lorry loader to hoist up machine 1ft above ground to check on balancing

- When well balanced, hoist up and load machine onto lorry chassis

- Release all sling from machine hoisting point

- Secured machine with strapping belt prior to moving out of customer premise

- Smaller item will be using forklift to load/unload onto lorry chassis

- Transport and deliver machine to new factory

- At new factory, hoist down machine from lorry chassis

- Insert rollers/pallet truck under machine bed

- Shift and transport machine into factory premise

- Position machine at the designated location

- Unload machine from rollers/pallet truck and insert levelling pad under machine bed

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175