# METHOD OF STATEMENT

Date: 19th July 2019

Description of work

To shift out 1 unit machine from production room to loading area, hoist up onto U Bed and deliver to new factory

Machine Spec

1 unit VL-1600ATC

Dim: 430 x 440 x 420 cm

Wt: 35, 000 kgs

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

25/07/2019   -   To jack up, insert rollers, shift and transfer to near door entrance

26/07/2019   -   To shift out machine to loading area, hoist up and load onto U Bed

27/07/2019   -   To unload machine from U bed, shift and position at the designated location

Time of Operation

09:30 am

Location of Operation

#### From 54 Loyang Way

#### To 182 Pandan Loop

MTQ Engineering Pte Ltd

Equipment Use

1 x 160 ton mobile crane

2 x lorry crane

1 x forklift

1 set hydraulic jack

Heavy duty rollers/pallet truck

Wire sling/webbing sling

Shackle

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and disposed

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crews certificate)

Safety Aspect

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Jack up machine to 4” high

- Insert rollers to machine base

- Shift out machine from production room to hoisting bay

- 160 ton mobile crane to hoist up machine and load onto U Bed

- Secured machine with strapping belt

- Transport and deliver machine to new location

- At new factory, hoist up and unload machine from U Bed to near ground level

- Insert rollers under machine base

- Shift machine into production area

- Position machine at the designated location

- Unload from rollers and insert levelling pad under machine bed

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd / Tel: 62824175