# METHOD OF STATEMENT

Date: 26th June 2023

Description of work

To shift out 1 unit machine with accessories from production to loading area, hoist and load onto wooden base for packing, after packing stuff onto low-bed/container

Machine Spec

1 unit Mazak Integrex E-650HS-II

Package 1 (Main machine): 1330 x 370 x 400 cm / N/G Wt: 45, 000 kg / 53, 800 kg

Package 2 (ATC): 520 x 170 x 355 cm / N/G Wt: 4, 100 kg / 6, 900 kg

Package 3 (Chip conveyor): 1250 x 180 x 215 cm / N/G Wt: 2, 400 kg / 5, 800 kg

Package 4 (Chiller): 130 x 122 x 165 cm / N/G Wt: 800 kg / 1, 500 kg

Package 5 (Electrical panel): 130 x 85 x 195 cm / N/G Wt: 1, 200 kg / 1, 800 kg

Package 6 (Control panel): 295 x 200 x 80 cm / N/G Wt: 1, 200 kg / 1, 700 kg

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

Estimate:

03/07/23 (move out & pack package 3-6)

04/07/23 (move out and pack package 2)

05/07/23 (to jack up machine & prepared for next day moving)

06/07/23 (move out machine for packing)

Time of Operation

10:00 am

Location of Operation

32 Tuas Ave 4

#### NTS Amega West Singapore Pte Ltd

Equipment Use

1 x 250 ton mobile crane

633 lorry loader

1 x forklift

Hydraulic rollers

4ton wire sling

15ton x 12m webbing sling

15ton wire sling

8.5-17 ton shackle

Spreader bar

Obstacles

No obstacle on loading and crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and disposed

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation

Safety Aspect

Access to be restricted to the site area, be cordoned off with safety cones, red/white tape and lifting in operation signage.

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet, safety harness)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Jack up machine to 4” high

- Insert hydraulic rollers under machine bed

- Shift out machine from production area

- Transport machine to designated hoisting/packing area

- To lay out wooden base for packing

- Attached lifting gears to crane hook and secured to rigging point of machine to be lifted

- 250 ton mobile crane to hoist up machine

- Load machine onto wooden base for packing

- Pack to form a case

- After packing, hoist up and load onto low-bed/container

- Secured case with choking wood and lashing wire

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175