# METHOD OF STATEMENT

Date: 14th Jan 2020

Description of Work

To assist engineer to dismantle Sound Proof Box. Jack machine to ground level and move it out of your premises to loading area. Hoist up onto trailer with lashing secure. Guide driver to leave your premises.

Machine Spec

1 unit Aida PMX Power Press

Est - Dim: 320 x 280 x 380cm – Wt: 45 ton

1 x Sound Proof Box

1 x Straightener

1 x NC Feeder

1 x Robot

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

17/01/20   -   Engineer to start dismantle sound proof box and jack machine up

18/01/20   -   Move machine our at your premises

Time of operation

09:45 am

Location of Operation

No 20 Benoi Sector

Shimano (S) Pte Ltd

Equipment Use

1 x 160 tons mobile crane

1 x 633 lorry loader

1 x 4.5 ton forklift

1 set heavy duty rollers

1 set 15ton wire sling

4 pcs 25ton shackle

4-8 pcs 17ton shackle

Obstacles

To clear all obstacles around working area

Barricade work area to prevent persons who are not involved enter unintentionally

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman, mobile/lorry crane operator and forklift operator will be involved in this operation

Safety Aspect

Barricade work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Assist Engineer to dismantle Sound Proof Box

- Jack machine up to ground level and lay metal plates

- Insert rollers below machine

- Use forklift to pull machine out from production to loading bay

- 160ton mobile crane to hoist up machine onto low loader

- Lower down machine slowly and let it sit onto wood block

- Secured machine firmly with belts

- Guide low loader driver out of customer premise

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and disposed

- Job complete

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175